## COVER
2020 WILDFIRE MITIGATION PLAN FINAL ACTION STATEMENT REFILING WITH QUARTERLY REPORT UPDATE
Attachment 1 Workbook (Tables 1 - 31) REDLINES
September 18, 2020
For the filed Wildfire Mitigation Plan (WMP) Attachment 1 Redline Workbook, BVES presents comparable changes made against BVES's May 22, 2020 Errata Filing (Errata), in which:
Red Text - updated values to the latest filed Errata submission;
Strikethrough - removed line item from the latest Errata submission; and
- New Cell and/or line item included since the filed Errata.
BVES also presents updates for its complete metrics tracking period of June 2019 - May 2020 pursuant to its approved 2019 WMP. Additional annual updates and programmatic activities are reflected in this filing to provide an accurate and current understanding of the utility's progress in reducing wildfire and PSPS risk by achieving project and program milestones. This 2020 WMP Refiling also includes responses to Class A and B deficiencies issued in Resolution WSD-006 and Draft Resolution WSD-010 satisfying information required in the quarterly report update as directed by the Final Action Statement on BVES's 2020 WMP refiling requirements. This workbook only reports on Attachment 1 required Tables (1-31).
Yellow Highlight

## >>WMP Section 1
Section 1 of the WMP narrative does not require reportable tables from Attachment 1.
Please see BVES's 2020 Final Action Statement WMP for developed responses.
This tab is informative only

## >>WMP Section 2
The following tabs correspond to Section 2 of the WMP Narrative
Please see BVES's 2020 Final Action Statement WMP for developed responses.
This tab is informative only

## Table 1
Table 1: Recent performance on progress metrics, last 5 years
| # | Progress metric name |  |  |  | Annual performance1 |  |  |  |  | Unit(s) | Comments
[6 empty] | 2015 | 2016 | 2017 | 2018 | 2019
| 1 | Grid condition findings from inspection | Findings per mile of circuit in HFTD | Level 1 |  | N/A - no data available at this time | N/A - no data available at this time | 0 | 0.018974 | 0.023718 | Number of Level 1, 2, and 3 findings per mile of circuit in HFTD, and per total miles of circuit for each of the following inspection types: 1. Patrol inspections 2. Detailed inspections 3. Other inspection types | Prior to 2017, inspection and other data which had been being maintained in a database system called Automated Line Patrol System (ALPS) were migrated to a new database system called “Partner.” While the old database has been archived and retained, data prior to 2017 is not readily available. During that transition, all level 1, 2 or 3 deficiencies had either been corrected or were entered into the new Partner system for tracking and remediation.
|  |  |  | Level 2 |  | N/A - no data available at this time | N/A - no data available at this time | 0 | 1.4563 | 2.2248
|  |  |  | Level 3 |  | N/A - no data available at this time | N/A - no data available at this time | 3.1687 | 0.28936 | 10.1276
|  |  | Findings per total circuit miles by inspection type | Patrol Inspections | Level 1 | N/A - no data available at this time | N/A - no data available at this time | 0 | 0.009487 | 0
[5 empty] | Level 2 | N/A - no data available at this time | N/A - no data available at this time | 0 | 0.60244 | 0.066411
[5 empty] | Level 3 | N/A - no data available at this time | N/A - no data available at this time | 3.1687 | 1.2855 | 1.5606
|  |  |  | Detailed Inspections2 | Level 1 | N/A - no data available at this time | N/A - no data available at this time | 0 | 0.018974 | 0.014231
[5 empty] | Level 2 | N/A - no data available at this time | N/A - no data available at this time | 0 | 1.4563 | 1.1764
[5 empty] | Level 3 | N/A - no data available at this time | N/A - no data available at this time | 0 | 0.28936 | 0.63564
|  |  |  | Other Inspection Types | Level 1 | N/A - no data available at this time | N/A - no data available at this time | 0 | 0.009487 | 0
[5 empty] | Level 2 | N/A - no data available at this time | N/A - no data available at this time | 0 | 0.60244 | 0.066411
[5 empty] | Level 3 | N/A - no data available at this time | N/A - no data available at this time | 0 | 1.2855 | 1.5606
| 2 | Vegetation clearance findings from inspection |  |  |  | N/A - no data available at this time | N/A - no data available at this time | N/A - no data available at this time | N/A - no data available at this time | 0.02 | Percentage of right-of-way with noncompliant clearance based on applicable rules and regulations at the time of inspection, as a percentage of all right-of-way inspected | 2019 figure is from October to December. Unable to locate any data prior to October 2019 with the granularity needed to respond.
| 3 | Extent of grid modularization | 1. In HFTD |  |  | 144 | 144 | 144 | 144 | 144 | Number of sectionalizing devices per circuit mile plus number of automated grid control equipment in: 1. HFTD 2. Non-HFTD | Entire BVES service territory is in HTFD 2 or 3.
|  |  | 2. In Non-HFTD |  |  | N/A - BVES does not have any portions of its service territory in Non-HFTD | N/A - BVES does not have any portions of its service territory in Non-HFTD | N/A - BVES does not have any portions of its service territory in Non-HFTD | N/A - BVES does not have any portions of its service territory in Non-HFTD | N/A - BVES does not have any portions of its service territory in Non-HFTD
| 4 | Data collection and reporting | [7 empty] | 97.1% | Percent of data requested in SDR and WMP collected in initial submission
Note: Values for Table 1.1 "Grid condition findings from inspection" were calculated by dividing the total number of findings of each type by the total number of overhead circuit miles in BVES's service territory, assuming underground circuits are unaffected by wind conditions. Including underground circuit miles in this calculation would deflate the actual assessment of risk posed by wind and other wildfire-risk conditions.
1. BVES tracks annual performance from June of the current year, through May of the following year, i.e. “2019” = June 2019 – May 2019.
2. Findings from detailed and patrol Inspections were not differentiated in the BVES’s database until 2018.

## Table 2
Table 2: Recent performance on outcome metrics, last 5 years
| Metric type | # | Outcome metric name | Annual performance |  |  |  |  | Unit(s) | Comments
|  |  |  | 2015 | 2016 | 2017 | 2018 | 2019
| 1. Near misses | 1.a. | Number of all events (such as unplanned outages, faults, conventional blown fuses, etc.) that could result in ignition, by type according to utility-provided list (total) | 33 | 85 | 83 | 31 | 25 | Number per year
|  | 1.b. | Number of all events (such as unplanned outages, faults, conventional blown fuses, etc.) that could result in ignition, by type according to utility-provided list (normalized) | 0.053664 | 0.028461 | 0.025065 | 0.013895 | 0.018726 | Number per RFW circuit mile day per year
|  | 1.c. | Number of wires down (total) | 7 | 17 | 4 | 3 | 3 | Number of wires down per year
|  | 1.d. | Number of wires down (normalized) | 0.011383 | 0.0056922 | 0.0012079 | 0.0013447 | 0.0022471 | Number per RFW circuit mile day per year
| 2. Utility inspection findings | 2.a. | Number of Level 1 findings that could increase the probability of ignition discovered per circuit mile inspected | N/A - no data available | N/A - no data available | 0 | 4 | 5 | Average number of Level 1 findings that could increase the probability of ignition discovered by all inspections per circuit mile per year | Prior to 2017, inspection and other data which had been being maintained in a database system called Automated Line Patrol System (ALPS) were migrated to a new database system called “Partner.” While the old database has been archived and retained, data prior to 2017 is not readily available. During that transition all level 1, 2 or 3 deficiencies had either been corrected or were entered into the new Partner system for tracking and remediation.
|  | 2.b. | Number of Level 2 findings that could increase the probability of ignition discovered per circuit mile inspected | N/A - no data available | N/A - no data available | 0 | 307 | 469 | Average number of Level 2 findings that could increase the probability of ignition discovered by all inspections per circuit mile per year
|  | 2.c. | Number of Level 3 findings that could increase the probability of ignition discovered per circuit mile inspected | N/A - no data available | N/A - no data available | 668 | 61 | 2135 | Average number of Level 3 findings that could increase the probability of ignition discovered by all inspections per circuit mile per year
| 3. Customer hours of PSPS and other outages | 3.a. | Customer hours of planned outages including PSPS (total) | 1467 | 2112 | 88412 | 6725 | 782 | Total customer hours of planned outages per year
|  | 3.b. | Customer hours of planned outages including PSPS (normalized) | 2.3856 | 0.70717 | 26.6993 | 3.0143 | 0.58574 | Total customer hours of planned outages per RFW circuit mile day per year
|  | 3.c. | Customer hours of unplanned outages, not including PSPS (total) | 73785 | 129310 | 155513 | 73619 | 121869 | Total customer hours of unplanned outages per year
|  | 3.d. | Customer hours of unplanned outages, not including PSPS (normalized) | 119.9887 | 43.2975 | 46.9629 | 32.9982 | 91.2836 | Total customer hours of unplanned outages per RFW circuit mile day per year
|  | 3.e. | Increase in System Average Interruption Duration Index (SAIDI) | 0 | 0 | 0 | 0 | 0 | Change in minutes compared to the previous year
| 4. Utility ignited wildfire fatalities | 4.a. | Fatalities due to utility-ignited wildfire (total) | 0 | 0 | 0 | 0 | 0 | Number of fatalities per year | BVES has not had any utility-ignited wildfires
|  | 4.b. | Fatalities due to utility-ignited wildfire (normalized) | 0 | 0 | 0 | 0 | 0 | Number of fatalities per RFW circuit mile day per year | BVES has not had any utility-ignited wildfires
| 5. Accidental deaths resulting from utility wildfire mitigation initiatives | 5.a. | Deaths due to utility wildfire mitigation activities (total) | 0 | 0 | 0 | 0 | 0 | Number of fatalities per year
| 6. OSHA-reportable injuries from utility wildfire mitigation initiatives | 6.a. | OSHA-reportable injuries due to utility wildfire mitigation activities (total) | 0 | 0 | 0 | 1 | 0 | Number of OSHA-reportable injuries per year | On July 19, 2018, a line worker and the owner of Teele Tree Services made contact with a high voltage power line and sustained non-fatal injuries. The injury did not require reporting under CalOSHA guidelines but BVES chose to report the incident.
|  | 6.b. | OSHA-reportable injuries due to utility wildfire mitigation activities (normalized) | 0 | 0 | 0 | 4.7436 | 0 | Number of OSHA-reportable injuries per year per 1000 line miles of grid | BVES has only 210.81 miles of OH lines. Navigant Consulting BVES interpreted this question to mean BVES would have 0.21081 "thousand line miles of grid."
| 7. Value of assets destroyed by utility-ignited wildfire, listed by asset type | 7.a. | Value of assets destroyed by utility-ignited wildfire (total) | 0 | 0 | 0 | 0 | 0 | Dollars of damage or destruction per year | BVES has not had any utility-ignited wildfires
|  | 7.b. | Value of assets destroyed by utility-ignited wildfire (normalized) | 0 | 0 | 0 | 0 | 0 | Dollars of damage or destruction per RFW circuit mile day per year | BVES has not had any utility-ignited wildfires
| 8. Structures damaged or destroyed by utility-ignited wildfire | 8.a. | Number of structures destroyed by utility-ignited wildfire (total) | 0 | 0 | 0 | 0 | 0 | Number of structures destroyed per year | BVES has not had any utility-ignited wildfires
|  | 8.b. | Number of structures destroyed by utility-ignited wildfire (normalized) | 0 | 0 | 0 | 0 | 0 | Number of structures destroyed per RFW circuit mile day per year | BVES has not had any utility-ignited wildfires
| 9. Acreage burned by utility-ignited wildfire | 9.a. | Acreage burned by utility-ignited wildfire (total) | 0 | 0 | 0 | 0 | 0 | Acres burned per year | BVES has not had any utility-ignited wildfires
|  | 9.b. | Acreage burned by utility-ignited wildfire (normalized) | 0 | 0 | 0 | 0 | 0 | Acres burned per RFW circuit mile day per year | BVES has not had any utility-ignited wildfires
| 10. Number of utility wildfire ignitions | 10.a. | Number of ignitions (total) according to existing ignition data reporting requirement | 0 | 0 | 0 | 0 | 0 | Number per year | BVES had not had any ignitions
|  | 10.b. | Number of ignitions (normalized) | 0 | 0 | 0 | 0 | 0 | Number per RFW circuit mile day per year | BVES had not had any ignitions
|  | 10.c. | Number of ignitions in HFTD (subtotal) | 0 | 0 | 0 | 0 | 0 | Number in HFTD per year | BVES had not had any ignitions
|  | 10.c.i. | Number of ignitions in HFTD Zone 1 | 0 | 0 | 0 | 0 | 0 | Number in HFTD Zone 1 per year | BVES had not had any ignitions
|  | 10.c.ii. | Number of ignitions in HFTD Tier 2 | 0 | 0 | 0 | 0 | 0 | Number in HFTD Tier 2 per year | BVES had not had any ignitions
|  | 10.c.iii. | Number of ignitions in HFTD Tier 3 | 0 | 0 | 0 | 0 | 0 | Number in HFTD Tier 3 per year | BVES had not had any ignitions
|  | 10.d. | Number of ignitions in HFTD (subtotal, normalized) | 0 | 0 | 0 | 0 | 0 | Number in HFTD per RFW circuit mile day per year | BVES had not had any ignitions
|  | 10.d.i. | Number of ignitions in HFTD Zone 1 (normalized) | 0 | 0 | 0 | 0 | 0 | Number in HFTD Zone 1 per RFW circuit mile day per year | BVES had not had any ignitions
|  | 10.d.ii. | Number of ignitions in HFTD Tier 2 (normalized) | 0 | 0 | 0 | 0 | 0 | Number in HFTD Tier 2 per RFW circuit mile day per year | BVES had not had any ignitions
|  | 10.d.iii. | Number of ignitions in HFTD Tier 3 (normalized) | 0 | 0 | 0 | 0 | 0 | Number in HFTD Tier 3 per RFW circuit mile day per year | BVES had not had any ignitions
|  | 10.e. | Number of ignitions in non-HFTD (subtotal) | 0 | 0 | 0 | 0 | 0 | Number in non-HFTD per year | BVES had not had any ignitions
|  | 10.f. | Number of ignitions in non-HFTD (normalized) | 0 | 0 | 0 | 0 | 0 | Number in non-HFTD per RFW circuit mile day per year | BVES had not had any ignitions
| 11. Critical infrastructure impacted | 11.a. | Critical infrastructure impacted by PSPS | 0 | 0 | 0 | 0 | 0 | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year | BVES has not needed to initiate any PSPS events
|  | 11.b. | Critical infrastructure impacted by PSPS (normalized) | 0 | 0 | 0 | 0 | 0 | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per RFW circuit mile day per year | BVES has not needed to initiate any PSPS events

## Table 3
Table 3: List and description of additional metrics, last 5 years
| Metric Category | Metric | Performance |  |  |  |  | Units | Underlying assumptions | Third-party validation
|  |  | 2015 | 2016 | 2017 | 2018 | 2019
| Overall Plan | Number of reportable fire incidents (D14-02-015 Appendix C: Fire Incident Data Collection Plan) | 0 | 0 | 0 | 0 | 0 | Number of incidents | Assess overall effectiveness of the plan | Prior to 2019, BVES was not required to record this data. 2015-2018 values based on review of utility records.
| Infrastructure | Number of bare line contact with vegetation | 6 | 39 | 17 | 9 | 5 | Number of contact events | Assess if plan has reduced risk events | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | Number of live wire down events | 7 | 17 | 4 | 3 | 1 | Number of events | Assess if plan has reduced risk events
|  | Number of conventional blown fuse events | 22 | 18 | 29 | 11 | 4 | Number of events | Assess if plan has reduced risk events
|  | Number of poles assessed | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 924 | 1588 | Number of poles | Determine if plan is on schedule
|  | Number of poles that failed assessment (wind loading, age, deterioraton, unfixable GO-95 violation) | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 655 | 393 | Numer of poles | Determine if plan is on schedule
|  | Number of poles replaced as a result of failed assessments | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 210 | 305 | Number of poles | Determine if plan is on schedule
|  | Number of poles remediated as a result of failed assessments | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 40 | 66 | Number poles | Determine if plan is on schedule
|  | Number of Tree Attachments Removed | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 230 | 199 | Number of attachments | Determine if plan is on schedule
|  | Number of new poles installed as a result of Tree Attachments Removed | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 9 | Number of poles | Determine if plan is on schedule
|  | Length of Covered Bare Wire (Circuit Miles) | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 0.52 | Length of wire (circuit miles) | Determine if plan is on schedule
|  | Number of conventional fuses replaced by current limiting fuses | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 285 | Number of fuses | Determine if plan is on schedule
|  | Number of conventional fuses replaced by fused trip savers (vacuum style) | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 9 | 8 | Number of fuses | Determine if plan is on schedule
| System Hardening | Number of Conventional fuses in system | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 1885 | Number of fuses | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | Percent of 34.5 kV System that is Overhead Bare Wire | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 97% | 95.9% | Percent of 34.5 kV circuit miles | Assess overall system hardening
|  | Percent of 34.5 kV System that is Underground | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 3% | 3% | Percent of 34.5 kV circuit miles | Assess overall system hardening
|  | Percent of 34.5 kV System that is Covered Wire | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 0% | 1.1% | Percent of 34.5 kV circuit miles | Assess overall system hardening
|  | Percent of 4 kV System that is Overhead Bare Wire | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 77.3% | 77.2% | Percent of 4 kV circuit miles | Assess overall system hardening
|  | Percent of 4 kV System that is Underground | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 22.7% | 22.7% | Percent of 4 kV circuit miles | Assess overall system hardening
|  | Percent of 4 kV System that is Covered Wire | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 0% | 0.1% | Percent of 4 kV circuit miles | Assess overall system hardening
|  | Number of Tree Attachments Remaining in System | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | N/A - metric not recorded prior to 2018 | 977 | 776 | Number of attachments | Assess overall system hardening
| Operations | Number of "Urgent" Vegetation Orders Issued (must be corrected w/30 days) | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 37 | Number of orders | Assess if vegetation management plan has reduced risk events | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | Number of "Urgent" Vegetation Orders Outstanding | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 0 | Number of orders | Determine if plan is on schedule
|  | Number of Trees Trimmed | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 5526 | 6671 | Number of trees | Determine if plan is on schedule
|  | Number of Trees Removed | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 80 | 123 | Number of trees | Determine if plan is on schedule
|  | Percent of OH System Cleared by Tree Trimming Crews | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 29% | 48% | Percent of OH system | Determine if plan is on schedule
|  | Number of Level 1 GO-95 Potential Non-Compliance (Immediate risk of high potential impact to safety or reliability) Items Idendified | N/A - metric not recorded prior to 2017 | N/A - metric not recorded prior to 2017 | 0 | 4 | 5 | Number of Items | Determine if plan is on schedule
|  | Number of Level 1 GO-95 Potential Non-Compliance (Immediate risk of high potential impact to safety or reliability) Items Outstanding | N/A - metric not recorded prior to 2017 | N/A - metric not recorded prior to 2017 | 0 | 0 | 0 | Number of Items | Determine if plan is on schedule
|  | Number of Level 2 GO-95 Potential Non-Compliance (Any other risk of at least moderate potential impact to safety or reliability) Items Idendified | N/A - metric not recorded prior to 2017 | N/A - metric not recorded prior to 2017 | 0 | 307 | 469 | Number of Items | Determine if plan is on schedule
|  | Number of Level 2 GO-95 Potential Non-Compliance (Any other risk of at least moderate potential impact to safety or reliability) Items Outstanding | N/A - metric not recorded prior to 2017 | N/A - metric not recorded prior to 2017 | 0 | 0 | 0 | Number of Items | Determine if plan is on schedule
|  | Number of Level 3 GO-95 Potential Non-Compliance (Any risk of low potential impact to safety or reliability) Items Idendified | N/A - metric not recorded prior to 2017 | N/A - metric not recorded prior to 2017 | 668 | 61 | 2135 | Number Items | Determine if plan is on schedule
|  | Number of Level 3 GO-95 Potential Non-Compliance (Any risk of low potential impact to safety or reliability) Items Outstanding | N/A - metric not recorded prior to 2017 | N/A - metric not recorded prior to 2017 | 0 | 0 | 0 | Number Items | Determine if plan is on schedule
|  | Number of Circuit Miles Patrolled per GO-165 | 211 | 211 | 211 | 211 | 422 | Number of Circuit Miles | Determine if plan is on schedule
|  | Number of Circuit Miles Inspected per GO-165 (detailed inspection) | 7.3 | 1.2 | 42.6 | 56.8 | 28.14 | Number of Circuit Miles | Determine if plan is on schedule
|  | Number of Poles Intrusively Inspected | 994 | 927 | 1013 | 155 | 48 | Number of Poles | Determine if plan is on schedule
|  | Number of Poles Failing Instrussive Inspection | 8 | 7 | 4 | 4 | 3 | Number of Poles | Determine if plan is on schedule
|  | Number of Circuit Miles of LiDAR Survey | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 211 | Number of Circuit Miles | Determine if plan is on schedule
|  | Number of LiDAR trouble spots1 | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 94 | Number of spots | Determine if plan is on schedule
|  | Number of Circuit Miles of Exacter Survey | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 120 | Number of Circuit Miles | Assess if communications plan has reduced customer concerns and risk events
|  | Number of Exacter trouble spots | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 10 | Number of trouble spots | Assess outage impact on customers as a result of PSPS
| Customer Service | Number of Customer Service Calls about Tree Trimming | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 0 | Number of Calls | Monitor changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | SAIDI due to PSPS | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 0 | System Average Interruption Duration Index | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
| Weather Conditions | Number of NFDRS “Very Dry” and “Dry” Days | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 150 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
| PSPS | Number of PSPS Events | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 0 | Number of Events | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | Maximum recorded sustained winds Recorded by NWS | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 41 | Miles per Hour | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Maximum recorded sustained winds Recorded by BVES Weather Stations | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 77.8 | Miles per Hour | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Maximum recorded wind gusts Recorded by NWS | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 53 | Miles per Hour | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Maximum recorded wind gusts Recorded by BVES Weather Stations | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 77.8 | Miles per Hour | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Frequency of sustained high winds (number of days sustained wind > 50 mph) recorded by NWS | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 0 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Frequency of sustained high winds (number of days sustained wind > 50 mph) recorded by BVES weather stations | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 5 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Frequency of high wind gusts (number of days wind gusts > 50 mph) recorded by NWS | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 1 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Frequency of high wind gusts (number of days wind gusts > 50 mph) recorded by BVES weather stations | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | N/A - metric not recorded prior to 2019 WMP | 5 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
Note: Data from 2015-2018 is unavailble for many as these metrics were not recorded prior to implementation of the current (2019) WMP, which took effect June 2019 .
1. Trouble spots defined as level 1 and 2 discrepancies

## Table 4
Table 4: List and description of program targets, last 5 years
| Metric Category | Metric | Program target | 2019 performance | Units | Underlying assumptions | Third-party validation
| Overall Plan | Number of reportable fire incidents (D14-02-015 Appendix C: Fire Incident Data Collection Plan) | 0 | 0 | Number of incidents | Assess overall effectiveness of the plan | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
| Infrastructure | Number of bare line contact with vegetation | <5 | 5 | Number of contact events | Assess if plan has reduced risk events | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | Number of live wire down events | <1 | 1 | Number of events | Assess if plan has reduced risk events
|  | Number of conventional blown fuse events | <5 | 4 | Number of events | Assess if plan has reduced risk events
|  | Number of poles assessed | 500 | 1588 | Number of poles | Determine if plan is on schedule
|  | Number of poles that failed assessment (wind loading, age, deterioraton, unfixable GO-95 violation) | N/A - this program does not have a specific target | 393 | Number of poles | Determine if plan is on schedule
|  | Number of poles replaced as a result of failed assessments | N/A - this program does not have a specific target | 305 | Number of poles | Determine if plan is on schedule
|  | Number of poles remediated as a result of failed assessments | N/A - this program does not have a specific target | 66 | Number poles | Determine if plan is on schedule
|  | Number of Tree Attachments Removed | 75 | 125 | Number of attachments | Determine if plan is on schedule
|  | Number of new poles installed as a result of Tree Attachments Removed | N/A - this program does not have a specific target | 9 | Number of poles | Determine if plan is on schedule
|  | Length of Covered Bare Wire (Circuit Miles) | 1 | 0.52 | Length of wire (circuit miles) | Determine if plan is on schedule
|  | Number of conventional fuses replaced by current limiting fuses | 1163 | 285 | Number of fuses | Determine if plan is on schedule
|  | Number of conventional fuses replaced by fused trip savers (vacuum style) | 230 | 8 | Number of fuses | Determine if plan is on schedule
| System Hardening | Number of Conventional fuses in system | N/A - this program does not have a specific target | 2493 | Number of fuses | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | Percent of 34.5 kV System that is Overhead Bare Wire | N/A - this program does not have a specific target | 95.9% | Percent of 34.5 kV circuit miles | Assess overall system hardening
|  | Percent of 34.5 kV System that is Underground | N/A - this program does not have a specific target | 3% | Percent of 34.5 kV circuit miles | Assess overall system hardening
|  | Percent of 34.5 kV System that is Covered Wire | N/A - this program does not have a specific target | 1.1% | Percent of 34.5 kV circuit miles | Assess overall system hardening
|  | Percent of 4 kV System that is Overhead Bare Wire | N/A - this program does not have a specific target | 77.2% | Percent of 4 kV circuit miles | Assess overall system hardening
|  | Percent of 4 kV System that is Underground | N/A - this program does not have a specific target | 2.7% | Percent of 4 kV circuit miles | Assess overall system hardening
|  | Percent of 4 kV System that is Covered Wire | N/A - this program does not have a specific target | 0.1% | Percent of 4 kV circuit miles | Assess overall system hardening
|  | Number of Tree Attachments Remaining in System | N/A - this program does not have a specific target | 776 | Number of attachments | Assess overall system hardening
| Operations | Number of "Urgent" Vegetation Orders Issued (must be corrected w/30 days) | N/A - this program does not have a specific target | 37 | Number of orders | Assess if vegetation management plan has reduced risk events | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | Number of "Urgent" Vegetation Orders Outstanding) | 0 | 0 | Number of orders | Determine if plan is on schedule
|  | Number of Trees Trimmed | N/A - this program does not have a specific target | 6671 | Number of trees | Determine if plan is on schedule
|  | Number of Trees Removed | N/A - this program does not have a specific target | 123 | Number of trees | Determine if plan is on schedule
|  | Percent of OH System Cleared by Tree Trimming Crews | 15% | 48% | Percent of OH system | Determine if plan is on schedule
|  | Number of Level 1 GO-95 Potential Non-Compliance (Immediate risk of high potential impact to safety or reliability) Items Idendified | 0 | 5 | Number of Items | Determine if plan is on schedule
|  | Number of Level 1 GO-95 Potential Non-Compliance (Immediate risk of high potential impact to safety or reliability) Items Outstanding | 0 | 0 | Number of Items | Determine if plan is on schedule
|  | Number of Level 2 GO-95 Potential Non-Compliance (Any other risk of at least moderate potential impact to safety or reliability) Items Idendified | <50 | 469 | Number of Items | Determine if plan is on schedule
|  | Number of Level 2 GO-95 Potential Non-Compliance (Any other risk of at least moderate potential impact to safety or reliability) Items Outstanding | 0 | 0 | Number of Items | Determine if plan is on schedule
|  | Number of Level 3 GO-95 Potential Non-Compliance (Any risk of low potential impact to safety or reliability) Items Idendified | < 1500 | 2135 | Number Items | Determine if plan is on schedule
|  | Number of Level 3 GO-95 Potential Non-Compliance (Any risk of low potential impact to safety or reliability) Items Outstanding | 0 | 0 | Number Items | Determine if plan is on schedule
|  | Number of Circuit Miles Patrolled per GO-165 | 118 | 422 | Number of Circuit Miles | Determine if plan is on schedule
|  | Number of Circuit Miles Inspected per GO-165 (detailed inspection) | 12 | 28.14 | Number of Circuit Miles | Determine if plan is on schedule
|  | Number of Poles Instrussively Inspected | 45 | 46 | Number of Poles | Determine if plan is on schedule
|  | Number of Poles Failing Instrussive Inspection | NA | 9 | Number of Poles | Determine if plan is on schedule
|  | Number of Circuit Miles of LiDAR Survey | 211 | 211 | Number of Circuit Miles | Determine if plan is on schedule
|  | Number of LiDAR trouble spots1 | N/A - this program does not have a specific target | 94 | Number of spots | Determine if plan is on schedule
|  | Number of Circuit Miles of Exacter Survey | <30 | 120 | Number of Circuit Miles | Assess if communications plan has reduced customer concerns and risk events
|  | Number of Exacter trouble spots | N/A - this program does not have a specific target | 10 | Number of trouble spots | Assess outage impact on customers as a result of PSPS
| Customer Service | Number of Customer Service Calls about Tree Trimming | N/A - this program does not have a specific target | 0 | Number of Calls | Monitor changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | SAIDI due to PSPS | N/A - this program does not have a specific target | 0 | System Average Interruption Duration Index | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
| Weather Conditions | Number of NFDRS “Very Dry” and “Dry” Days | N/A - this program does not have a specific target | 150 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
| PSPS | Number of PSPS Events | N/A - this program does not have a specific target | 0 | Number of Events | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status.
|  | Maximum recorded sustained winds Recorded by NWS | N/A - this program does not have a specific target | 41 | Miles per Hour | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Maximum recorded sustained winds Recorded by BVES Weather Stations | N/A - this program does not have a specific target | 77.8 | Miles per Hour | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Maximum recorded wind gusts Recorded by NWS | N/A - this program does not have a specific target | 53 | Miles per Hour | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Maximum recorded wind gusts Recorded by BVES Weather Stations | N/A - this program does not have a specific target | 77.8 | Miles per Hour | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Frequency of sustained high winds (number of days sustained wind > 50 mph) recorded by NWS | N/A - this program does not have a specific target | 0 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Frequency of sustained high winds (number of days sustained wind > 50 mph) recorded by BVES weather stations | N/A - this program does not have a specific target | 5 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Frequency of high wind gusts (number of days wind gusts > 50 mph) recorded by NWS | N/A - this program does not have a specific target | 1 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
|  | Frequency of high wind gusts (number of days wind gusts > 50 mph) recorded by BVES weather stations | N/A - this program does not have a specific target | 5 | Number of Days | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns
Note: The “2019 Performance” column only captures data from June 2019 (2019 WMP implementation start) to May 2020. Some "Program Targets" are estimates for current actuals based on June 2019-January 2020 performance.
1. Trouble spots defined as level 1 and 2 discrepancies

## Table 5
Table 5: Accidental deaths due to utility wildfire mitigation initiatives, last 5 years
| Activity | Victim | [14 empty] | Total
|  | Full-time employee |  |  |  |  | Contractor |  |  |  |  | Member of public
| Year | 2015 | 2016 | 2017 | 2018 | 2019 | 2015 | 2016 | 2017 | 2018 | 2019 | 2015 | 2016 | 2017 | 2018 | 2019
| Inspection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Vegetation management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Utility fuel management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grid hardening | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Table 6
Table 6: OSHA-reportable injuries due to utility wildfire mitigation initiatives, last 5 years
| Activity | Victim | [14 empty] | Total
|  | Full-time employee |  |  |  |  | Contractor |  |  |  |  | Member of public
| Year | 2015 | 2016 | 2017 | 2018 | 2019 | 2015 | 2016 | 2017 | 2018 | 2019 | 2015 | 2016 | 2017 | 2018 | 2019
| Inspection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Vegetation management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Utility fuel management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grid hardening | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Note: On July 19, 2018, a line worker and the owner of Teele Tree Services made contact with a high voltage power line and sustained non-fatal injuries. The injury did not require reporting under Cal/OSHA guidelines but BVES chose to report the incident.

## Table 7
Table 7: Methodology for potential impact of ignitions
| List of all data inputs used in impact simulation | Sources of data inputs | Data selection and treatment methodologies | Assumptions, including SME input | Equation(s), functions, or other algorithms used to obtain output | Output type(s), e.g., wind speed model | Comments
| N/A - BVES does not have a proprietary model or methodology for evaluating the potential impact of ignitions. BVES's Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. BVES will investigate the ability to develop this methodology going forward. | N/A - BVES does not have a proprietary model or methodology for evaluating the potential impact of ignitions. BVES's Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. BVES will investigate the ability to develop this methodology going forward. | N/A - BVES does not have a proprietary model or methodology for evaluating the potential impact of ignitions. BVES's Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. BVES will investigate the ability to develop this methodology going forward. | N/A - BVES does not have a proprietary model or methodology for evaluating the potential impact of ignitions. BVES's Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. BVES will investigate the ability to develop this methodology going forward. | N/A - BVES does not have a proprietary model or methodology for evaluating the potential impact of ignitions. BVES's Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. BVES will investigate the ability to develop this methodology going forward. | N/A - BVES does not have a proprietary model or methodology for evaluating the potential impact of ignitions. BVES's Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. BVES will investigate the ability to develop this methodology going forward. | N/A - BVES does not have a proprietary model or methodology for evaluating the potential impact of ignitions. BVES's Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. BVES will investigate the ability to develop this methodology going forward.
Note: Bear Valley Electric Service does not have a proprietary model or methodology for evaluating the potential impact of ignitions. BVES’s Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores.

## Table 8
Table 8: Map file requirements for recent and modelled conditions of utility service territory, last 5 years
| Layer name | Measurements | 2015 | 2016 | 2017 | 2018 | 2019 | Average | Units | Attachment location | Comments
| Recent weather patterns | Average annual number of Red Flag Warning days per square mile across service territory | 0.091156 | 0.44272 | 0.49088 | 0.33072 | 0.19791 | 0.31067 | Area, days, square mile resolution | N/A - BVES is unable to provide this data at this time | BVES's service territory is 32 square miles
|  | Average 95th percentile wind speed and prevailing direction (actual) | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time | Area, miles per hour, at a square mile resolution or better, noting where measurements are actual or interpolated |  | BVES is unable to provide this data for each year at this time.
|  | Average 99th percentile wind speed and prevailing direction (actual) | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time | N/A - BVES is unable to provide this data at this time
| Recent drivers of ignition probability | Date of recent ignitions categorized by ignition probability driver | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | Point, GPS coordinate, days, square mile resolution | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | BVES has not had any recent ignitions
| Recent use of PSPS | Duration of PSPS events and area of the grid affected in customer hours per year | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | Area, customer hours, square mile resolution | N/A - No event of this type occurred during the 2015 - 2019 period; not applicable. | BVES has not had any recent use of PSPS
Note: BVES is unable to provide the above requested data in GIS map file format at this time.BVES has no non-HFTD territory, i.e., the territory is completing within the HFTD and include entirely rural communities respective to the WUI designations.

## Table 9
Table 9: Map file requirements for baseline condition of utility service territory projected for 2020
| Layer Name | Measurements/Variables | Value | Unit(s) | Appendix Location
| Current baseline state of service territory and autility equipment | Non-HFTD vs HFTD (Zone 1, Tier 2, Tier 3) regions of utility service territory | Non-HFTD: NA Zone 1: NA Tier 2: 112.38 Tier 3: 5.48 | Area, square mile resolution per type | N/A - BVES does not have this information at thist ime
|  | Urban vs. rural vs. highly rural regions of utility service territory | Very Rural: NA Rural: 102.24 Urban: 22.58 | Area, square mile resolution per type
|  | WUI regions of utility service territory | WUI Flag Based on 2010 Data 0 (Non-WUI): 87.75 1 (Intermix): 15.79 2 (Interface): 21.27 | Area, square mile resolution per type
| Layer Name | Measurements/Variables | Critical Facility | Address | GPS Coordinate | Unit(s) | Appendix Location
| Current baseline state of service territory and autility equipment | Number and location of critical facilities | City of Big Bear Lake (CBBL) | 39707 Big Bear Blvd. Big Bear Lake, CA | 34.238138, -116.935334 | Point, GPS Coordinate | N/A
|  |  | Big Bear Fire Department | 41090 Big Bear Blvd. Big Bear Lake CA | 34.244454, -116.905308
|  |  | Mountaintop Ranger District, U.S. Forest Service | 41374 North Shore Drive, Hiway 38 Fawnskin, CA 92333 | 34.263421, -116.900904
|  |  | San Bernardino County Sherriff's Deparment Big Bear Lake Patrol Station | 477 Summit Blvd. Big Bear Lake, CA 92315 | 34.243900, -116.887824
|  |  | Big Bear Area Regional Wastewater Agency (BBARWA) | 121 Palomino Dr, Big Bear City, CA 92314 | 34.267869, -116.814973
|  |  | Big Bear City Community Services District (CSD) | 139 E. Big Bear Blvd. Ca 92314 | 34.261530, -116.844248
|  |  | Big Bear Lake Water Department (DWP) | 41972 Garstin Dr. Big Bear Lake, CA 92315 | 34.246650, -116.886294
|  |  | Big Bear Municipal Water District (MWD) | 40524 Lakeview CT, Big Bear Lake, CA 92315 | 34.242787, -116.917948
|  |  | Southwest Gas Corporation | 140 Business Center Dr. Big Bear Lake, CA 92315 | 34.249530, -116.888579
|  |  | Bear Valley Community Hospital | 41870 Garstin Dr. Big Bear Lake, Ca 92315 | 34.246529, -116.881211
|  |  | Bear Valley Unified School District | 42271 Moonridge Rd. CA 92315 | 34.242345, -116.881211
|  |  | Big Bear Chamber of Commerce | 630 Bartlett Rd. Big Bear Lake, CA 92315 | 34.241133, -116.912336
|  |  | Big Bear Airport District | 501 W. Valley Blvd. Big Bear City, CA 92314 | 34.261844, -116.853605
|  |  | Big Bear Mountain Resort/ Summit | 880 Summit Blvd. Big Bear Lake, Ca 92315 | 34.236417, -116.889272
| Layer Name | Measurements/Variables | Value | Unit(s) | Appendix Location
| Current baseline state of service territory and autility equipment | Number and location of customers | 186.81 Customers / Sq Mi | Area, number of people, square mile resolution | N/A - Footnote (which is presented below is not cited)
|  | Numer and Location of customers belonging to acces and functional needs populations | N/A - BVES does not have this information at thist ime | Area, number of people, square mile resolution
|  | Overhead transmission lines | N/A - BVES does not have this information at thist ime | Line, quarter mile resolution
|  | Overhead distribution lines | N/A - BVES does not have this information at thist ime | Line, quarter mile resolution
| Layer Name | Measurement/svariables | Weather Station Name | Address | GPS Coordinates | Unit(s) | Appendix Location
| Current baseline state of service territory and utility equipment | Location of Substations | Bear City Sub | 322 West Meadow Ln. Big Bear city, 92314 | 34.265381, -116.849596 | Point, GPS Coordinate | 6.4
|  |  | Bear Mountain Sub | Lassen Dr, 1500 Ft W/O Primrose dr. big Bear City, 92314 | 34.224328, -116.857868
|  |  | Division Sub | 150' W/O Division Dr. Big Bear Lake, 92314 | 34.261855, -116.866588
|  |  | Fawnskin Sub | S/E Corner of Mast Dr. Big Bear Lake, 92314 | 34.261406, -116.882163
|  |  | Lake Sub | Garstin Dr. N/O Fox Farm Rd, Big Bear Lake, 92315 | 34.253290, -116.891879
|  |  | Maltby Sub | S/E Corner of Maltby Blvd. & Shore Dr. Big Bear City, 92314 | 34.266335, -116.830982
|  |  | Maple Sub | N/O Baldwin Ln & 500' W/O Maple Ln. Big Bear City, 92314 | 34.250630, -116.827014
|  |  | Meadow Sub | N/O 42020 Garstin Dr. Big Bear Lake, 92315 | 34.247049, -116.885375
|  |  | Moonridge Sub | S/E Corner of Clubview Dr. & Clover Dr. Big Bear Lake, 92315 | 34.226772, -116.863810
|  |  | Palomino Sub | N/O Shay Rd & E/O Palomino Dr. Big Bear City, 92314 | 34.268660, -116.814846
|  |  | Pine Knot Sub | S/E Corner of Lahontan Dr. & Georgia St. Big Bear Lake, 92315 | 34.245323, -116.900342
|  |  | Summit Sub | S/W Corner of Summit Blvd, Snow Summit Parking Lot, Big Bear Lake 92315 | 34.236216, -116.889647
|  |  | Village Sub | 150' W/O Knickerbocker Rd Big Bear Lake, 92315 | 34.240145, -116.910389
| Layer Name | Measurement/svariables | Weather Station Name | Latitude | Longitude | Pole # | Unit(s) | Appendix Location
| Current baseline state of service territory and utility equipment | Location of Weather Stations | Boulder | 34.2386 | -116.9376 | 12524BV | Point, GPS Coordinate | N/A
|  |  | Radford | 34.2018 | -116.9055 | 12188BV
|  |  | Clubview | 34.2403 | -116.868 | 13117BV
|  |  | Garstin | 34.2463 | -116.8876 | 13050BV
|  |  | Erwin | 34.233 | -116.7921 | 12671BV
|  |  | Sunrise | 34.2545 | -116.8239 | 9784BV
|  |  | North Shore | 34.2453 | -116.9735 | 6984BV
|  |  | Lagonita | 34.2473 | -116.9351 | 11054BV
|  |  | Goldmine | 34.2294 | -116.8426 | 7319BV
|  |  | Baldwin | 34.2938 | -116.8131 | 10170BV
|  |  | Pioneer | 34.2632 | -116.7907 | 11967BV
|  |  | Paradise | 34.2665 | -116.8401 | 11000BV
|  |  | Division | 34.2619 | -116.8667 | 13090BV
|  |  | Fawnskin | 34.2638 | -116.9344 | 12535BV
|  |  | Big Bear Dam | 34.2422 | -116.9777 | 1210284CTC
|  |  | Sugarloaf | 34.243 | -116.8374 | 5026BV
|  |  | Lake Williams | 34.232 | -116.7733 | 9607BV
|  |  | Erwin Lake | 34.2429 | -116.8007 | 7025BV
|  |  | 2N10 | 34.2165 | -116.9074 | 4254BV
|  |  | Bertha Park | Bertha Peak | 34.283 | 116.8994
| Layer Name | Measurement/svariables | Value | Unit(s) | Appendix Location
| Current baseline state of service territory and utility equipment | All utility assets by asset type, model, age, specifications, and condition | See Section 61 | Point, GPS Coordinate | BVES has provided some of this information. See Section 6 and the GIS attachment file for more information
| Layer Name | Measurement/svariables | Value | Unit(s) | Appendix Location
| Location of planned utility equipment additions or removal | Non-HFTD vs HFTD (Zone 1, Tier 2, Tier 3) regions of utility service territory | N/A - BVES does not have this information at thist ime | Line, quarter mile resolution | BVES does not have this information at this time. BVES plans to submit this data in future filings.
|  | Urban vs. rural vs. highly rural regions of utility service territory | N/A - BVES does not have this information at thist ime | Line, quarter mile resolution
|  | WUI regions of utility service territory | N/A - BVES does not have this information at thist ime | Line, quarter mile resolution
|  | Circuit miles of overhead transmission lines | N/A - BVES does not have this information at thist ime | Line, quarter mile resolution
|  | Circuit miles of overhead distribution lines | N/A - BVES does not have this information at thist ime | Line, quarter mile resolution
|  | Location of substations | N/A - BVES does not have this information at thist ime | Point, GPS coordinate
| Layer Name | Measurement/svariables | Value | Unit(s) | Appendix Location
| Planned 2020 WMP initiative activity per year | Location of 2020 WMP initiative activity for each activity as planned to be completed by the end of each year of the plan term | See Section 6 | Line, quarter mile resolution | BVES has provided some of this information. See Section 6 and the GIS attachment file for more information
Note: BVES is unable to provide most of the data requestd in GIS format at this time. The GIS file(s) provided with this WMP submission include information on customer distribution location of all utility assets such as distribution lines (the utility does not operate any transmission lines according to the Commission's definition thereof), substations, generating facilities, switches, etc.
Where such data cannot be provided in GIS format at this time, the utility has provided the data it can in the tables below. Line items in blue text under "Location of Weather Stations" represent planned future additions.
Note: BVES has submitted this data in its GIS filing. BVES plans to calculate this data in subsequent filings.
BVES is working on identifying functional needs populations and will provide this information in subsequent filings. BVES is also in the process of calculating the its overhead transmission and distribution lines and will provide this information in subsequent filings.
1. BVES has provided some of this information. See Section 6 and the GIS attachment file for more information

## >>WMP Section 3
The following tabs correspond to Section 3 of the WMP Narrative
Please see BVES's 2020 Final Action Statement WMP for developed responses.
This tab is informative only

## Table 10
Table 10: Weather patterns, last 5 years
| Weather measurement | 2015 | 2016 | 2017 | 2018 | 2019 | 5-year historical average | Unit(s)
| Red Flag Warning days | 614.9328 | 2986.5453 | 3311.4035 | 2231.0022 | 1335.0597 | 2095.7887 | RFW circuit mile days per year
| Days rated at the top 30% of proprietary fire potential index or similar fire risk index measure | 107 | 151 | 118 | 129 | 87 | 118.4 | Circuit mile days where proprietary measure rated above top 30% threshold per year
| 95th percentile wind conditions | 5691.87 | 8221.59 | 8643.21 | 6956.73 | 14967.51 | 8896.182 | Circuit mile days with wind gusts over 95th percentile historical (meaning the prior 10 years, 2005-2014) conditions per year
| 99th percentile wind conditions | 1897.29 | 2318.91 | 2318.91 | 1686.48 | 6535.11 | 2951.34 | Circuit mile days with wind gusts over 99th percentile historical (meaning the prior 10 years, 2005-2014) conditions per year
| Other | N/A - Bear Valley Electric Service cannot provide data on any other weather patterns to the specificity requested at this time | N/A - Bear Valley Electric Service cannot provide data on any other weather patterns to the specificity requested at this time | N/A - Bear Valley Electric Service cannot provide data on any other weather patterns to the specificity requested at this time | N/A - Bear Valley Electric Service cannot provide data on any other weather patterns to the specificity requested at this time | N/A - Bear Valley Electric Service cannot provide data on any other weather patterns to the specificity requested at this time | N/A - Bear Valley Electric Service cannot provide data on any other weather patterns to the specificity requested at this time | N/A - Bear Valley Electric Service cannot provide data on any other weather patterns to the specificity requested at this time
Note: A third-party assessed the NFDRS and estimated fire ratings of Brown ("Very Dry") or more severe as falling within the top 30% of the NFDRS. When calculating circuit-mile days, the contractor multiplied the corresponding metric (RFW days, 95th/99th percentile wind conditions days) by the total number of overhead circuit miles in BVES’s service territory, assuming that underground circuit miles are unaffected by wind conditions. Including underground circuit miles in this calculation would deflate the actual assessment of risk posed by wind and other wildfire-risk conditions. When a Red Flag Warning is issued for the San Bernardino Mountains, including Big Bear Valley, which encompasses the entirety of BVES’s service territory, the Warning applies to 100 percent of BVES’s service territory. BVES will be updating this information, including additional historical data, in the next iteration of its WMP. BVES plans to supplement future WMP submittals with additional weather information from its weather stations as they are added to the databases.

## Table 11
Table 11: Key recent drivers of ignition probability, last 5 years
| Incident type by ignition probability driver |  | Near misses tracked (y/n)? | Number of incidents per year | [5 empty] | Average percentage probability of ignition per incident | [5 empty] | Number of ignitions per year from this driver
|  |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average
| Contact from object | All types of object contact | Y | 6 | 35 | 12 | 8 | 4 | 13 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Animal contact | Y | 0 | 0 | 1 | 1 | 1 | 0.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Balloon contact | Y | 0 | 1 | 0 | 0 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Veg. contact | Y | 6 | 34 | 11 | 7 | 3 | 12.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Vehicle contact | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| All types of equipment / facility failure | All types | Y | 40 | 40 | 42 | 23 | 16 | 32.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Capacitor bank failure | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductor failure—all | Y | 0 | 3 | 0 | 0 | 3 | 1.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductor failure—wires down | Y | 0 | 3 | 0 | 0 | 3 | 1.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Fuse failure—all | Y | 18 | 15 | 20 | 12 | 4 | 13.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Fuse failure—conventional blown fuse | Y | 18 | 15 | 20 | 10 | 4 | 13.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Lightning arrestor failure | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Switch failure | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformer failure | Y | 4 | 4 | 2 | 1 | 2 | 2.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Wire-to-wire contact / contamination |  | Y | 0 | 0 | 1 | 1 | 2 | 0.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Other |  | Y | 0 | 1 | 0 | 0 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Note: In 2018, an umbrella was caught in one of BVES's overhead distribution lines.

## Table 12
Table 12: Recent use of PSPS, last 5 years
| PSPS characteristic | 2015 | 2016 | 2017 | 2018 | 2019 | Unit(s)
| Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| Frequency of PSPS events (normalized) | 0 | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof in order to reduce ignition probability, per RFW circuit mile day per year
| Scope of PSPS events (total) | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
| Scope of PSPS events (normalized) | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | Circuit-events, measured in number of events multiplied by number of circuits targeted for de-energization per RFW circuit mile day per year
| Duration of PSPS events (total) | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | Customer hours per year
| Duration of PSPS events (normalized) | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | N/A - BVES did not have any PSPS events in this year | Customer hours per RFW circuit mile day per year
| Other | N/A - no other PSPS-related data to report | N/A - no other PSPS-related data to report | N/A - no other PSPS-related data to report | N/A - no other PSPS-related data to report | N/A - no other PSPS-related data to report | N/A - no other PSPS-related data to report
Note: 1. BVES did not implement a PSPS event over the 2015-2019 period.
Note: 2. No other relevant PSPS-related data to report.

## Table 13
Table 13: Current baseline state of service territory and utility equipment
| Land use | Characteristic tracked | In non-HFTD | In HFTD Zone 1 | In HFTD Tier 2 | In HFTD Tier 3
| In urban areas | Circuit miles | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of critical facilities | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of critical facilities in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers belonging to access and functional needs populations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers belonging to access and functional needs populations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
| In rural areas | Circuit miles | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of critical facilities | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of critical facilities in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers belonging to access and functional needs populations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers belonging to access and functional needs populations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
| In highly rural areas | Circuit miles | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of critical facilities | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of critical facilities in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers belonging to access and functional needs populations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of customers belonging to access and functional needs populations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
Supporting Table 3-1
|  | Land use | Characteristic tracked | In non-HFTD | In HFTD Zone 1 | In HFTD Tier 2 | In HFTD Tier 3
|  | Service Area | Circuit miles | 0 | 0 | 262.2 | 2.8
|  | (see note above) | Number of critical facilities | 0 | 0 | 14 | 0
|  |  | Number of customers | 0 | 0 | 24511 | 0
|  |  | Number of customers belonging to access and functional needs populations | 0 | 0 | 202 | 0
|  |  | Circuit miles of overhead transmission lines | 0 | 0 | 0 | 0
|  |  | Circuit miles of overhead distribution lines | 0 | 0 | 208.1 | 2.8
|  |  | Number of substations | 0 | 0 | 13 | 0
Note: Supporting Table 3-1 has been provided that shows aggregated characteristics of the BVES system. Future filings will provide further granularity as BVES expands its data collection for future plan updates.
BVES does not have any transmission lines as all of its lines are below 65 kV.

## Table 14
Table 14: Summary data on weather station count
| Weather station count type | Current count | Unit(s)
| Number of weather stations (total) | 18 | Total number located in service territory and operated by utility
| Number of weather stations (normalized) | 0.0853 | Total number located in service territory and operated by utility, divided by total number of circuit miles in utility service territory
| Number of weather stations in non-HFTD (total) | 0 | Total number located in non-HFTD service territory and operated by utility
| Number of weather stations in non-HFTD (normalized) | 0 | Total number located in non-HFTD service territory and operated by utility, divided by total number of circuit miles in non-HFTD service territory
| Number of weather stations in HFTD Zone 1 (total) | 0 | Total number located in HFTD Zone 1 service territory and operated by utility
| Number of weather stations in HFTD Zone 1 (normalized) | 0 | Total number located in HFTD Zone 1 service territory and operated by utility, divided by total number of circuit miles in HFTD Zone 1 service territory
| Number of weather stations in HFTD Tier 2 (total) | 17 | Total number located in HFTD Tier 2 service territory and operated by utility
| Number of weather stations in HFTD Tier 2 (normalized) | 0.08183 | Total number located in HFTD Tier 2 service territory and operated by utility, divided by total number of circuit miles in HFTD Tier 2 service territory
| Number of weather stations in HFTD Tier 3 (total) | 1 | Total number located in HFTD Tier 3 service territory and operated by utility
| Number of weather stations in HFTD Tier 3 (normalized) | 0.354 | Total number located in HFTD Tier 3 service territory and operated by utility, divided by total number of circuit miles in HFTD Tier 3 service territory
Note: BVES's service territory is entirely rural and either HFTD Tier 2 or Tier 3.
Circuit miles were calculated as the total overhead circuit miles, assuming that underground circuit miles are unaffected by wind conditions. Including underground circuit miles in this calculation would deflate the actual assessment of risk posed by wind and other wildfire-risk conditions.

## Table 15
Table 15: Summary data on fault indicator count
| Fault indicator count type | Current count | Unit(s)
| Number of fault indicators (total) | 87 | Total number located in service territory and operated by utility
| Number of fault indicators (normalized) | 0.4127 | Total number located in service territory and operated by utility, divided by total number of circuit miles in utility service territory
| Number of fault indicators in non-HFTD (total) | 0 | Total number located in non-HFTD service territory and operated by utility
| Number of fault indicators in non-HFTD (normalized) | 0 | Total number located in non-HFTD service territory and operated by utility, divided by total number of circuit miles in non-HFTD service territory
| Number of fault indicators in HFTD Zone 1 (total) | 0 | Total number located in HFTD Zone 1 service territory and operated by utility
| Number of fault indicators in HFTD Zone 1 (normalized) | 0 | Total number located in HFTD Zone 1 service territory and operated by utility, divided by total number of circuit miles in HFTD Zone 1 service territory
| Number of fault indicators in HFTD Tier 2 (total) | 87 | Total number located in HFTD Tier 2 service territory and operated by utility
| Number of fault indicators in HFTD Tier 2 (normalized) | 0.4152 | Total number located in HFTD Tier 2 service territory and operated by utility, divided by total number of circuit miles in HFTD Tier 2 service territory
| Number of fault indicators in HFTD Tier 3 (total) | 0 | Total number located in HFTD Tier 3 service territory and operated by utility
| Number of fault indicators in HFTD Tier 3 (normalized) | 0 | Total number located in HFTD Tier 3 service territory and operated by utility, divided by total number of circuit miles in HFTD Tier 3 service territory
Note: BVES's service territory is entirely rural and either HFTD Tier 2 or Tier 3.
Circuit miles were calculated as the total overhead circuit miles, assuming that underground circuit miles are unaffected by wind conditions. Including underground circuit miles in this calculation would deflate the actual assessment of risk posed by wind and other wildfire-risk conditions.

## Table 16
Table 16: Location of planned utility equipment additions or removal by end of 3-year plan term
| Land use | Characteristic tracked | Changes by end-2022
|  |  | In non-HFTD | In HFTD Zone 1 | In HFTD Tier 2 | In HFTD Tier 3
| In urban areas | Circuit miles of overhead transmission lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | 0
|  | Circuit miles of overhead distribution lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | 0
|  | Circuit miles of overhead distribution lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of weather stations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of weather stations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
| In rural areas | Circuit miles of overhead transmission lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | 0
|  | Circuit miles of overhead distribution lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | 0
|  | Circuit miles of overhead distribution lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of weather stations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of weather stations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
| In highly rural areas | Circuit miles of overhead transmission lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of weather stations | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of weather stations in WUI | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
Transmission lines refer to all lines at or above 65 kV, and distribution lines refer to all lines below 65 kV.
Note: BVES does not own transmission lines and all of its lines are below 65kV. BVES does not plan to add or remove any overhead distribution lines. BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings.

## Table 17
Table 17: Location of planned utility infrastructure upgrades
| Land use | Characteristic tracked | In non-HFTD |  |  | In HFTD Zone 1 |  |  | In HFTD Tier 2 |  |  | In HFTD Tier 3
|  |  | 2020 | 2021 | 2022 | 2020 | 2021 | 2022 | 2020 | 2021 | 2022 | 2020 | 2021 | 2022
| Total circuit miles planned for hardening each year, all types and locations |  | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | 3.5 | 12.9 | 12.9 | 0 | 2.8 | 0
| Total number of substations planned for hardening each year, all locations |  | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | N/A - Bear Valley Electric Service's entire Service Territory is in HFTD 2 or 3 | 1 | 0 | 0 | 0 | 0 | 0
| In urban areas | Circuit miles planned for grid hardening of overhead transmission lines | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
| In rural areas | Circuit miles of overhead transmission lines to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
| In highly rural areas | Circuit miles of overhead transmission lines to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead distribution lines in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Circuit miles of overhead transmission lines in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
|  | Number of substations in WUI to harden | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type | N/A - BVES has provided GIS data on its WUI, urban, and rural areas in alignment with data from the Spatial Analysis for Conservation and Sustainability (SILVIS) Lab at the University of Wisconsin-Madison and the US Census Bureau, respectively. BVES plans to update its GIS database and will refresh this information in future WMP filings broken out by WUI land use type
Transmission lines refer to all lines at or above 65 kV, and distribution lines refer to all lines below 65 kV.
Note: BVES does not have any transmission lines as all of its lines are below 65 kV.
BVES does not track which portions of its distribution system and other utilty-owned infrastructure or assets are located in WUI-designated areas.
The utility does not have any urban or highly rural areas noted specifically at this time. BVES's service territory is considered rural.

## Table 18
Table 18: Key drivers of ignition probability
| Ignition probability drivers |  | Number of incidents per year (according to 5-year historical average) | Average likelihood of ignition per incident | Ignitions from this driver (according to 5-year historical average)
[5 empty] | Total | In non-HFTD | In HFTD Zone 1 | In HFTD Tier 2 | In HFTD Tier 3
| Contact from object | All types of object contact | 13 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Animal contact | 0.6 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Balloon contact | 0.2 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Vegetation contact | 12.2 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Vehicle contact | 0 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
| All types of equipment / facility failure | All types | 32.2 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Capacitor bank failure | 0 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Conductor failure—all | 1.2 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Conductor failure—wires down | 1.2 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Fuse failure—all | 13.8 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Fuse failure—conventional blown fuse | 13.4 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Lightning arrestor failure | 0 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Switch failure | 0 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
|  | Transformer failure | 2.6 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
| Wire-to-wire contact / contamination |  | 0.8 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
| Other |  | 0.2 | 0% | 0 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | N/A - BVES's entire Service Territory is either HFTD 2 or 3 | 0 | 0
Note: BVES's service territory is in either HFTD Tier 2 or Tier 3. None is within the non-HFTD or Zone 1.

## >>WMP Section 4
The following tabs correspond to Section 4 of the WMP Narrative
Please see BVES's 2020 Final Action Statement WMP for developed responses.
This tab is informative only

## Table 19
Table 19: Macro trends impacting ignition probability and/or wildfire consequence
| Rank | Macro trends impacting utility ignited ignition probability and estimated wildfire consequence by year 10 | Comments
| 1 | Change in ignition probability and estimated wildfire consequence due to climate change | BVES expects climate change to produce significant increase in ignition probability over the 10-year period. Based on 2017 Climate Change and Health Profile Report San Bernardino County (UC Davis), California Fourth Climate Assessment.
| 3 | Change in ignition probability and estimated wildfire consequence due to relevant invasive species, such as bark beetles | The Big Bear Lake region has previously been affected by bark beetles, notably in the Summer of 2018 as a result of the then-ongoing drought in California. While BVES has not experienced any ignition events, increased dead tree density is likely as climate change creates more favorable Summer conditions for bark beetle populations.
| 2 | Change in ignition probability and estimated wildfire consequence due to other drivers of change in fuel density and moisture | BVES's service territory is in a heavily forested alpine environment. Any increase in fuel density and dryness creates a disproportionate increase in ignition probability and/or estimated wildfire consequences.
| 5 | Population changes (including Access and Functional Needs population) that could be impacted by utility ignition | BVES's service territory is entirely in a mountain resort region. BVES does not expect significant population changes within its service territory and does not foresee measurable changes impacting ignition probability and/or wildfire consequence as a result.
| 6 | Population changes in HFTD that could be impacted by utility ignition | BVES's service territory is entirely in a mountain resort region. BVES does not expect significant population changes within its service territory and does not foresee measurable changes impacting ignition probability and/or wildfire consequence as a result.
| 4 | Population changes in WUI that could be impacted by utility ignition | BVES's service territory is entirely in a mountain resort region. BVES does not expect significant population changes within its service territory and does not foresee measurable changes impacting ignition probability and/or wildfire consequence as a result.
| 7 | Utility infrastructure location in HFTD vs non-HFTD | BVES's service territory is entirely in HFTD 2 or HFTD3. As a result, BVES does not foresee any differentiated impacts in ignition probability and/or wildfire consequence due to the location of utilit infrastructure in HFTD vs non-HFTD
| 8 | Utility infrastructure location in urban vs rural vs highly rural areas | BVES's service territory is primarily rural with no highly rural areas and limited urban areas. As a result, BVES does not foresee any differentiated impacts in ignition probability and/or wildfire consequences due to the location of utility infrastructure in urban vs rural vs highly rural areas

## Table 20
Table 20: Anticipated characteristics of PSPS use over next 10 years
| Rank order 1-9 | PSPS characteristic | Significantly increase; increase; no change; decrease; significantly decrease | Comments
| N/A - BVES does not anticipate and has not had any PSPS events | Number of customers affected by PSPS events (total) | No change | BVES has not implemented any PSPS and does not anticipate the need for PSPS over the next 10 years
| N/A - BVES does not anticipate and has not had any PSPS events | Number of customers affected by PSPS events (normalized by fire weather, e.g., Red Flag Warning line mile days) | No change | BVES has not implemented any PSPS and does not anticipate the need for PSPS over the next 10 years
| N/A - BVES does not anticipate and has not had any PSPS events | Frequency of PSPS events in number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability (total) | No change | BVES has not implemented any PSPS and does not anticipate the need for PSPS over the next 10 years
| N/A - BVES does not anticipate and has not had any PSPS events | Frequency of PSPS events in number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability (normalized by fire weather, e.g., Red Flag Warning line mile days) | No change | BVES has not implemented any PSPS and does not anticipate the need for PSPS over the next 10 years
| N/A - BVES does not anticipate and has not had any PSPS events | Scope of PSPS events in circuit-events, measured in number of events multiplied by number of circuits targeted for de-energization (total) | No change | BVES has not implemented any PSPS and does not anticipate the need for PSPS over the next 10 years
| N/A - BVES does not anticipate and has not had any PSPS events | Scope of PSPS events in circuit-events, measured in number of events multiplied by number of circuits targeted for de-energization (normalized by fire weather, e.g., Red Flag Warning line mile days) | No change | BVES has not implemented any PSPS and does not anticipate the need for PSPS over the next 10 years
| N/A - BVES does not anticipate and has not had any PSPS events | Duration of PSPS events in customer hours (total) | No change | BVES has not implemented any PSPS and does not anticipate the need for PSPS over the next 10 years
| N/A - BVES does not anticipate and has not had any PSPS events | Duration of PSPS events in customer hours (normalized by fire weather, e.g., Red Flag Warning line mile days) | No change | BVES has not implemented any PSPS and does not anticipate the need for PSPS over the next 10 years
| N/A - BVES does not anticipate and has not had any PSPS events | Other | No change | BVES has not implemented any PSPS and does not anticipate the need for PSPS over the next 10 years
Note: BVES does not anticipate future PSPS events to occur and has not initiated proactive de-energization within 2015 - 2019.

## >>WMP Section 5
The following tabs correspond to Section 5 of the WMP Narrative
Please see BVES's 2020 Final Action Statement WMP for developed responses.
This tab is informative only

## Table 21
Table 21: Risk assessment and mapping
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | 2019 plan | Bear Valley Electric Service has implemented the CPUC Fire-Threat Map Adopted in D17-12-024 December 14, 2017 throughout its service territory. This map shows the CPUC-designated fire hazard zone tiers within BVES' service territory, which quantify specific geography that could be subject to elevated fire risk under historically viable fire weather conditions. BVES has also identified seven sections of "at-risk" areas within its service territory based on the type of distribution facilities (overhead bare conductors, high voltage, etc.), tree and vegetation density, available dry fuel, and other factors that make certain locations more vulnerable to wildfire risk. The “at-risk” line sections are shown and further outlined in BVES's WMP submission. BVES' wildfire mapping efforts are foundational to determing and executing on priorities amongst the utilities's risk mitigation efforts as well as its day-to-day operations. BVES employs tier designations to inform inspection, vegetation management, correction timeframes, and prioritized hardening efforts. Wildfire risk mapping is foundational to prioritizing efforts for a variety of activities undertaken throughout the business. Bear Valley Electric Service does not have a summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment. Within the next 3 years, BVES will develop a summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment There are no specifically designated expenses, risk reductions, or any of the other column headings above associated with this initiative. Within the next 3 years, BVES will endeavor to develop a cost estimate to develop the model and present the estimated costs as part of its WMP filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Climate-driven risk map and modelling based on various relevant weather scenarios | 2019 plan | Bear Valley Electric Service has implemented the CPUC Fire-Threat Map Adopted in D17-12-024 December 14, 2017 throughout its service territory. This map shows the CPUC-designated fire hazard zone tiers within BVES' service territory, which quantify specific geography that could be subject to elevated fire risk under historically viable fire weather conditions. BVES has also identified seven sections of "at-risk" areas within its service territory based on the type of distribution facilities (overhead bare conductors, high voltage, etc.), tree and vegetation density, available dry fuel, and other factors that make certain locations more vulnerable to wildfire risk. The “at-risk” line sections are shown and further outlined in BVES's WMP submission. BVES' wildfire mapping efforts are foundational to determing and executing on priorities amongst the utilities's risk mitigation efforts as well as its day-to-day operations. BVES employs tier designations to inform inspection, vegetation management, correction timeframes, and prioritized hardening efforts. Wildfire risk mapping is foundational to prioritizing efforts for a variety of activities undertaken throughout the business. Bear Valley Electric Service does not have a climate-driven risk map and modelling based on various relevant weather scenarios. Within the next 3 years, BVES will endeavor to develop a climate-driven risk map and modelling based on various relevant weather scenarios. There are no specifically designated expenses, risk reductions, or any of the other column headings above associated with this initiative. Within the next 3 years, BVES will develop a cost estimate to develop the model and present the estimated costs as part of its WMP filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 2019 plan | Bear Valley Electric Service has implemented the CPUC Fire-Threat Map Adopted in D17-12-024 December 14, 2017 throughout its service territory. This map shows the CPUC-designated fire hazard zone tiers within BVES' service territory, which quantify specific geography that could be subject to elevated fire risk under historically viable fire weather conditions. BVES has also identified seven sections of "at-risk" areas within its service territory based on the type of distribution facilities (overhead bare conductors, high voltage, etc.), tree and vegetation density, available dry fuel, and other factors that make certain locations more vulnerable to wildfire risk. The “at-risk” line sections are shown and further outlined in BVES's WMP submission. BVES' wildfire mapping efforts are foundational to determing and executing on priorities amongst the utilities's risk mitigation efforts as well as its day-to-day operations. BVES employs tier designations to inform inspection, vegetation management, correction timeframes, and prioritized hardening efforts. Wildfire risk mapping is foundational to prioritizing efforts for a variety of activities undertaken throughout the business. Bear Valley Electric Service does not have an ignition probability mapping showing the probability of ignition along the electric lines and equipment. Within the next 3 years, BVES will endeavor to develop an ignition probability mapping showing the probability of ignition along the electric lines and equipment. There are no specifically designated expenses, risk reductions, or any of the other column headings above associated with this initiative. Within the next 3 years, BVES will develop a cost estimate to develop the model and present the estimated costs as part of its WMP filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 2019 plan | Bear Valley Electric Service has implemented the CPUC Fire-Threat Map Adopted in D17-12-024 December 14, 2017 throughout its service territory. This map shows the CPUC-designated fire hazard zone tiers within BVES' service territory, which quantify specific geography that could be subject to elevated fire risk under historically viable fire weather conditions. BVES has also identified seven sections of "at-risk" areas within its service territory based on the type of distribution facilities (overhead bare conductors, high voltage, etc.), tree and vegetation density, available dry fuel, and other factors that make certain locations more vulnerable to wildfire risk. The “at-risk” line sections are shown and further outlined in BVES's WMP submission. BVES' wildfire mapping efforts are foundational to determing and executing on priorities amongst the utilities's risk mitigation efforts as well as its day-to-day operations. BVES employs tier designations to inform inspection, vegetation management, correction timeframes, and prioritized hardening efforts. Wildfire risk mapping is foundational to prioritizing efforts for a variety of activities undertaken throughout the business. Bear Valley Electric Service does not have an initiative mapping and estimation of wildfire and PSPS risk-reduction impact. Within the next 3 years, BVES will endeavor to develop an Initiative “mapping and estimation of wildfire and PSPS risk-reduction impact” There are no specifically designated expenses, risk reductions, or any of the other column headings above associated with this initiative. Within the next 3 years, BVES will develop a cost estimate to develop the model and present the estimated costs as part of its WMP filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 2019 plan | Bear Valley Electric Service does not, at this time, have a specific wilfire mitigation risk assessment and mapping initiative focused on conducting match drop simulations showing the potential wildfire consequence of ignitions that occur along BVES's electric lines and equipment. BVES's Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. There are not specifically designated expenses, risk reductions, or any of the other column headings above associated with this initiative. Within the next 3 years, BVES will develop a cost estimate to develop the model and present the estimated costs as part of its WMP filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Weather-driven risk map and modelling based on various relevant weather scenarios | 2019 plan | Bear Valley Electric Service has implemented the CPUC Fire-Threat Map Adopted in D17-12-024 December 14, 2017 throughout its service territory. This map shows the CPUC-designated fire hazard zone tiers within BVES' service territory, which quantify specific geography that could be subject to elevated fire risk under historically viable fire weather conditions. BVES has also identified seven sections of "at-risk" areas within its service territory based on the type of distribution facilities (overhead bare conductors, high voltage, etc.), tree and vegetation density, available dry fuel, and other factors that make certain locations more vulnerable to wildfire risk. The “at-risk” line sections are shown and further outlined in BVES's WMP submission. BVES' wildfire mapping efforts are foundational to determing and executing on priorities amongst the utilities's risk mitigation efforts as well as its day-to-day operations. BVES employs tier designations to inform inspection, vegetation management, correction timeframes, and prioritized hardening efforts. Wildfire risk mapping is foundational to prioritizing efforts for a variety of activities undertaken throughout the business. Bear Valley Electric Service does not have a weather driven risk map and model based on various relevant weather scenarios. BVES subject matter expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. Within the next 3 years, BVES will endeavor to develop a weather-driven risk map and modelling based on various relevant weather scenarios. There are no specifically designated expenses, risk reductions, or any of the other column headings above associated with this initiative. Within the next 3 years, BVES will develop a cost estimate to develop the model and present the estimated costs as part of its WMP filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 7. Other / not listed | 2019 plan | Bear Valley Electric Services does not have any risk assessment and mapping initiatives other than those provided above at this time. Within the next 3 years, BVES will develop a cost estimate to develop the model and present the estimated costs as part of its WMP filing.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 22
Table 22: Situational awareness and forecasting
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. Advanced weather monitoring and weather stations | 2019 plan | 122000 | 122000 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Dry conditions, high wind speeds, inclement weather that could increase ignition risk (e.g. lightning) | 1024621.77 | 8.4 | Wildfire-Significant Loss of Property | Existing | GRC | Memorandum Account and GRC | In compliance | GO95 | Installs additional 10 weather stations throughout the BVES service area bringing the total to 20 weather stations. Allows BVES to prepare response ahead of time and take precautionary and/or advanced action. Also, allows BVES to validate actual conditions in the field such as before and after PSPS events.
|  | 2019 actual | 103136 | 103136 | 0
|  | 2020 | 0 | 0 | 0
|  | 2021 | 0 | 0 | 0
|  | 2022 | 0 | 0 | 0
|  | 2020-2022 plan total | 0 | 0 | 0
| 2. Continuous monitoring sensors | 2019 plan | 0 | 0 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 994609.51 | 3.98 | Wildfire-Significant Loss of Property | New | N/A - this is a new initiative | WMP Memorandum Account | Exceeding compliance | GO95 | Installs ALERT Wildfire HD Cameras throughout the service area allowing rapid detection and direction of first responders to any fires.
|  | 2019 actual | 0 | 0
|  | 2020 | 250000 | 250000 | 0
|  | 2021 | 250000 | 250000 | 0
|  | 2022 | 0 | 0 | 0
|  | 2020-2022 plan total | 500000 | 500000 | 0
| 3. Fault indicators for detecting faults on electric lines and equipment | BVES is monitoring Down wire Detection Technology and once the technology is ready for field use, BVES will develop a Down Wire Detection Installment Program in future WMPs.
| 4. Forecast of a fire risk index, fire potential index, or similar | 2019 plan | Bear Valley Electric Service has not established a plan to develop a forecast of a fire risk index, fire potential index, or similar beyond that which it has communicated in its 2019 and 2020 WMPs at this time. BVES's Subject Matter Expert evaluates the frequency of potential ignition events versus a set of impact categories (reliability, compliance, quality of service, safety and environmental) to develop total risk impact and scores. In addition, no specific incremental spend has been identified for this initiative. Bear Valley Electric Service does not have a proprietary model or methodology for evaluating the potential impact of ignitions.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation situational awareness and forecasting initiative focused on personnel monitoring areas of electric lines and equipment in elevated fire risk conditions in addition to the situational awareness and forecasting initiatives described in Table 22 as well as the asset management and inspection initiatives described in Table 24. During high fire threat weather that could lead to PSPS events, BVES does deploy crews to monitor conditions in the field, in the high threat areas.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Weather forecasting and estimating impacts on electric lines and equipment | 2019 plan | 45000 |  | 45000 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 1022629.33 | 14.52 | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | New | N/A - this is a new initiative | WMP Memorandum Account | Exceeding compliance | ESRB-8 | Weather Consulting Services. Provides BVES staff service area specific forecasts to better understand possible fire threat weather as well as storm conditions that may affect service. Allows BVES to prepare response ahead of time and take precautionary and/or avoidance action. Est. $45,000 O&M annually.
|  | 2019 actual | 19000 | 0 | 19000
|  | 2020 | 45000 | 0 | 45000
|  | 2021 | 45000 | 0 | 45000
|  | 2022 | 45000 | 0 | 45000
|  | 2020-2022 plan total | 135000 | 0 | 135000
| 7. Other / not listed | 2019 plan | 0 | 0 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Dry conditions, high wind speeds, inclement weather that could increase ignition risk (e.g. lightning) | 1143068.47 | 3.34 | Wildfire-Significant Loss of Property. | New | N/A - this is a new initiative | WMP Memorandum Account | Exceeding compliance | ESRB-8 | Project. Installs complete Distribution Management Control Center with the following equipment and applications that provide full information capabilities available to Distribution decision makers relevant to the following functional areas: (1) Energy Resources (2) T&D Assets (3) SCADA, Outage Management System & GIS Other Applications (4) Weather Information (5) HD Cameras (6) Media access (Internet, BVES Website & Social Media, Local Radio, TV, etc. (7) Communications Equipment and (8) Dispatch services.
|  | 2019 actual | 0 | 0 | 0
|  | 2020 | 0 | 0 | 0
|  | 2021 | 0 | 0 | 0
|  | 2022 | 0 | 0 | 0
|  | 2020-2022 plan total | 0 | 0 | 0
| 8. Other / not listed | 2019 plan | 0 | 0 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 148458.96 | 3.2 | Wildfire-Significant Loss of Property. Loss of Energy Supplies. | Existing | D 19-08-027 | GRC | Exceeding compliance | ESRB-8 | GIS-based applications (e.g. Outage Management System).Implementation of GIS-based systems, such as outage management systems and interactive voice response systems, which allow BVES to locate outages and respond to customers more promptly in the case of a wildfire or related emergency
|  | 2019 actual | 0 | 0 | 0
|  | 2020 | 54799.92 |  | 54799.92
|  | 2021 | 55895.92 |  | 55895.92
|  | 2022 | 57013.84 |  | 57013.84
|  | 2020-2022 plan total | 167709.68 |  | 167709.68
| 9. Other/ not listed | 2019 plan | $ $70,000 | $ $70,000 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from Object. All types of equipment/facility failure, wire-wire contact/contamination | 148458.96 | 2.19 | Wildfire-Significant Loss of Property | New | N/A - this is a new initiative | GRC | Exceeding compliance | ESRB-8 | Implement iRestore APP.Provides First Responders and internal Damage Assessment Teams tool to quickly document and report T&D facility problems to Dispatch.
|  | 2019 actual | $67,860.00 | $ 67,860.00 | 0
|  | 2020 | 0 | 0 | 0
|  | 2021 | 0 | 0 | 0
|  | 2022 | 0 | 0 | 0
|  | 2020-2022 plan total | 0 | 0 | 0

## Table 23
Table 23: Grid design and system hardening
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. Capacitor maintenance and replacement program | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation grid design and system hardening initiative focused on capacitor maintenance and replacement at this time. Bear Valley Electric Service has 25 capacitor locations and maintenance and replacement is included in the company's standard inspection, maintenance, and replacement protocols. The capacitors are fixed (either on service or off service) and part of our Overhead Facility Patrol and Inspection program objectives is to ensure they are not leaking or visually damaged. Any enhanced inspections or accelerated correction timeframe/replacements are captured in Table 24 Asset management and inspections.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation grid design and system hardening initiative focused on circuit breaker maintenance and replacement at this time. Circuit breakers are generally installed for all distribution circuits to detect fault current and protect equipment in the event that a fault is detected. Circuit breaker replacement and maintenance is included in the company’s standard inspection, maintenance, and replacement protocols. Any enhanced inspections or accelerated correction timeframe/replacements are captured in Table 24 Asset management and inspections. Replacements of specific, targeted circuit breakers as a part of BVES' WMP to support overall advanced coordination and detection efforts are better captured in Table 23 Initiative 9. Installation of system automation equipment.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Covered conductor installation | 2019 plan | 458000 | 458000 | $ - | 6 | 76333 | Contact from object. | 872292.38 | 0.48 | Wildfire-Significant Loss of Property | New | N/A - request by approval of 2020 WMP | WMP Memorandum Account | N/A - this initiative is not associated with specific regulations. The program exceeds standard design. | N/A - this initiative is not associated with a specific rule | 2019 includes $458,000 for the Covered Conductor Replacement Pilot Program and $292,000 for the Covered Conductor Wrap Pilot Program. Program replaces all 205.2 line miles of 34.5 kV overhead sub-transmission lines (beginning in 2020) and 4 kV distribution lines (beginning in 2021) with covered wire over a 6-year period, 2020-2025.
|  | 2019 actual | 350191 | 350191 | $ - | 6 | 58365
|  | 2020 | 1832933 | 1832933 | $ - | 15 | 122196
|  | 2021 | 5345970 | 5345970 | $ - | 40.8 | 131029
|  | 2022 | 5345970 | 5345970 | $ - | 40.8 | 131029
|  | 2020-2022 plan total | 12524873 | 12524873 | $ - | 96.6 | 129657
| 4. Covered conductor maintenance | 2019 plan | Bear Valley Electric Service does not have specific wildfire mitigation grid design and system hardening initiatives focused on covered conductor maintenance. As BVES progresses with its implementation of its wildfire mitigation initiatives, BVES will continue to evaluate covered conductor maintenance initiatives specific to wildfire mitigation.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Crossarm maintenance, repair, and replacement | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation grid design and system hardening initiative focused on crossarm maintenance, repair, and replacement at this time. Routine crossarm maintenance, repair, and replacement are included in the company’s standard inspection and correction programs, with an accelerated timeline for correction under the company’s Inspection program improvement, as included in Table 24 Asset management and inspections.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Distribution pole replacement and reinforcement, including with composite poles | 2019 plan | 2444130 | 2444130 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | All types of equipment/facility failure, wire-wire contact/contamination | 872292.38 | 0.36 | Wildfire-Significant Loss of Property | Existing | D. 19-08-027 | GRC | In compliance with Regulation | GO-95 | Test all poles to loading standards, GO95 requirements, intrusive inspection criteria and age and then, replaces or remediates non-compliant poles.
|  | 2019 actual | 5096681 | 5096681 | 0
|  | 2020 | 2444130 | 2444130 | 0
|  | 2021 | 2444130 | 2444130 | 0
|  | 2022 | 2444130 | 2444130 | 0
|  | 2020-2022 plan total | 7332390 | 7332390 | 0
| 7. Expulsion fuse replacement | 2019 plan | 2600000 | 2600000 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Fuse failure-all. | 872292.38 | 0.34 | Wildfire-Significant Loss of Property | New | N/A - this is an existing initiative | WMP Memorandum Account | Exceeds | GO 95 | Replaces all conventional (expulsion) fuses with current limiting (ELF) and electronic fuses (Fuse TripSavers).
|  | 2019 actual | 1303306 | 1303306 | 0
|  | 2020 | 2600000 | 2600000 | 0
|  | 2021 | 0 | 0 | 0
|  | 2022 | 0 | 0 | 0
|  | 2020-2022 plan total | 2600000 | 2600000 | 0
| 8. Grid topology improvements to mitigate or reduce PSPS events | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation grid design and system hardening initiative focused on grid topology improvements to mitigate or reduce PSPS events in addition to those described elsewhere in Table 23 such as Initiatives 16(a)-16(f).
2019 actual
2020
2021
2022
2020-2022 plan total
| 9. Installation of system automation equipment | 2019 plan | 1073541 | 1073541 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 1148135.45 | 0.59 | Wildfire-Significant Loss of Property. Loss of Energy Supplies | Existing | D. 19-08-027 | GRC | N/A - this initiative is not associated with a specific regulation | N/A - this initiative is not associated with a specific rule | Install grid automation. Fully instruments and automates BVES grid. Consists of installing a service area wide network operating on a SCADA system, substation automation, remote fault indicators, remote metering and power sensors and remote switching equipment to enable BVES to significantly improve its capability to detect and isolate faults rapidly before ever rolling out a crew. 8% complete as of January 2020.
|  | 2019 actual | 612829 | 612829 | 0
|  | 2020 | 953159 | 953159 | 0
|  | 2021 | 939156 | 939156 | 0
|  | 2022 | 915833 | 915833 | 0
|  | 2020-2022 plan total | 2808148 | 2808148 | 0
| 10. Maintenance, repair, and replacement of connectors, including hotline clamps | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation grid design and system hardening initiative focused on maintenance, repair, and replacement of connectors, including hotline clamps at this time. Replacement of connectors, where applicable, is included in other programs such as installation of covered conductor.
2019 actual
2020
2021
2022
2020-2022 plan total
| 11. Mitigation of impact on customers and other residents affected during PSPS event | 2019 plan | Bear Valley Electric Service does not have specific wildfire mitigation grid design and system hardening initiatives focused on mitigation of impact on customers and other residents affected during PSPS event in addition to the initiatives in Table 23. Both of these programs are combined as relevant grid topology improvements pertaining to grid design and system hardening that reduce PSPS events inherently also mitigate the impact on customers. Furthermore,BVES’s additional programs or efforts to mitigate the impact on customers and other residents affected during a PSPS event are captured in Table 28 Item 5.
2019 actual
2020
2021
2022
2020-2022 plan total
| 12. Other corrective action | 2019 plan | 0 | 0 | 0 | 0 | 0 | Contact from object. Conductor failure-all. | 1148135.45 | 0.22 | Wildfire-Significant Loss of Property. Wildfire-Public Safety. | New | N/A - this is a new initiative | WMP Memorandum Account | Exceeds | GO 95 | Replaces the 34.5 kV Radford Line (2.82 overhead circuit miles/8.46 line miles) with covered power lines and poles that are resistant to fire.
|  | 2019 actual | 0 | 0 | 0 | 0 | 0
|  | 2020 | 156236 | 156236 | 0 | 0 | Costs for design
|  | 2021 | 5443764 | 5443764 | 0 | 8.46 | 661938.5343
|  | 2022 | 0 | 0 | 0 | 0 | 0
|  | 2020-2022 plan total | 5600000 | 5600000 | 0 | 8.46 | 661938.5343
| 13. Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 2019 plan | Bear Valley Electric Service's pole loading infrastructure hardening and replacement program based on pole loading assessment program is encompassed by and addressed in Table 24 Initiative 6. Intrusive pole inspections. Under this initiative, BVES tests all poles to loading standards, GO95 requirements, intrusive inspection criteria and age, and then replaces or remediates non-compliant poles.
2019 actual
2020
2021
2022
2020-2022 plan total
| 14. Transformers maintenance and replacement | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation grid design and system hardening initiative focused on transformer maintenance and replacement. Transformer replacement and maintenance is included in the company’s standard inspection, maintenance, and replacement protocols. .
2019 actual
2020
2021
2022
2020-2022 plan total
| 15. Transmission tower maintenance and replacement | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation grid design and system hardening initiative focused on transmission tower maintenance and replacement because BVES does not own any transmission.
2019 actual
2020
2021
2022
2020-2022 plan total
| 16. Undergrounding of electric lines and/or equipment | 2019 plan | The SCE Ute Lines (1 & 2), which only serve BVES, consists of approximately 1.5 miles of overhead sub-transmission bare lines (34.5 kV) that connect the BVES system at two points with the SCE Goldhill Switch Station. The Ute Lines (1 & 2) run on the same poles for a large section of the circuit. These SCE assets are located in the U.S. Forest Service area and in an environmentally sensitive area known as the “pebble plane”. These lines provide approximately 72% of rated supply capacity and, under normal conditions, 100% of BVES’ supply loads. These lines allow BVES to adopt a defensive operational scheme during the fire season by allowing the de-energization of the Radford Line (from the Redlands), which mostly traverses a High Fire Threat District (“HFTD”) Tier 3 area. The Ute Lines (1 & 2) are completely in a HFTD Tier 2 area. Therefore, these lines are critical to BVES’ energy supply and reliability and permit BVES to significantly mitigate risk of wildfire in its HFTD Tier 3 area. BVES does not intend to pursue this project further, but intends to pursue other options with SCE to resolve the inherent wildfire risk exposure, and system safety and reliability risk of the Ute lines. Under this WMP, BVES does not propose to underground any overhead lines.
2019 actual
2020
2021
2022
2020-2022 plan total
| 17. Updates to grid topology to minimize risk of ignition in HFTDs | 2019 plan | Bear Valley Electric Service does not have any specific grid design and system hardening wildfire mitigation initiatives focused on updates to grid topology to minimize risk of ignition in HFTDs at this time. BVES recognizes that it should continue to evaluate updates to grid topology as weather patterns change and overall modeling and assessments evolve. Other grid design and system hardening programs include, as a component, grid topology improvements to minimize the risk of ignition in the HFTD. BVES recognizes that it is challenging to mitigate wildfire risk through grid topology changes alone and therefore focuses more on augmentation of existing circuitry through system hardening efforts included throughout Table 23.
2019 actual
2020
2021
2022
2020-2022 plan total
| 18. Other / not listed | 2019 plan | 0 | 0 | 0 | N/A - this initiative does not have a specific line mileage associated with its implementation | N/A - this initiative does not have a specific line mileage associated with its implementation | Contact from object. All types of equipment/facility failure. | 1143070.47 | 0.72 | Wildfire-Significant Loss of Property. | Existing | D. 19-08-027 | GRC | N/A - this initiative is not associated with a specific regulation | N/A - this initiative is not associated with a specific rule | Safety and Technical Upgrades to Palomino Substation. Converts substation from overhead-type to underground and pad-mounted design with deadfront SCADA enabled equipment.
|  | 2019 actual | 0 | 0 | 0
|  | 2020 | 1587675 | 1587675 | 0
|  | 2021 | 0 | 0 | 0
|  | 2022 | 0 | 0 | 0
|  | 2020-2022 plan total | 1587675 | 1587675 | 0
| 19. Other / not listed | 2019 plan | 2936929 | 2936929 |  | N/A - this initiative does not have a specific line mileage associated with its implementation | N/A - this initiative does not have a specific line mileage associated with its implementation | Contact from object. All types of equipment/facility failure. | 1143068.47 | 0.39 | Wildfire-Significant Loss of Property. | Existing | D. 19-08-027 | GRC | N/A - this initiative is not associated with a specific regulation | N/A - this initiative is not associated with a specific rule | Safety and Technical Upgrades to Pineknot substation. Converts substation from overhead-type to underground and pad-mounted design with deadfront SCADA enabled equipment. Estimated $2,936,929.00 CAPEX over 1 year 2019-2020. 90% complete as of January 2020. Covered in BVES' General Rate Case A.17-05-004.
|  | 2019 actual | 3524748 | 3524748 | 0
|  | 2020 | 0 | 0 | 0
|  | 2021 | 0 | 0 | 0
|  | 2022 | 0 | 0 | 0
|  | 2020-2022 plan total | 0 | 0 | 0
| 20. Other / not listed | 2019 plan | 732018 | 732018 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object. All types of equipment/facility failure. Wire-to-wire contact/contamination. | 1146143.02 | 1.57 | Wildfire-Significant Loss of Property. Wildfire-Public Safety. | Existing | D. 19-08-027 | GRC | Exceeding | GO 95 | Replaces all tree attachments in the BVES service area with overhead on poles. Covered in BVES' General Rate Case A.17-05-004.
|  | 2019 actual | 701348 | 701348 | 0
|  | 2020 | 732018 | 732018 | 0
|  | 2021 | 732018 | 732018 | 0
|  | 2022 | 732018 | 732018 | 0
|  | 2020-2022 plan total | 2196054 | 2196054 | 0
| 21. Other / not listed | 2019 plan | 0 | 0 | 0 | N/A | N/A | Wildfire-Public Safety. | 1022629.33 | 0.6 | Wildfire-Significant Loss of Property | New | N/A - this is a new initiative | WMP Memorandum Account | N/A - this initiative is not associated with a specific regulation | N/A - this initiative is not associated with a specific rule | Hardening of overhead facilities along evacuation routes to prevent facilities from falling into evacuation routes during a wildfire. Pilot program to be perform in 2020 plan at a cost of $200,000. Note that the estimates for 2021 and 2022 will be updated in next WMP based on pilot program results.
|  | 2019 actual | 0 | 0 | 0
|  | 2020 | 200000 | 200000 | 0
|  | 2021 | 1710000 | 1710000 | 0
|  | 2022 | 1710000 | 1710000 | 0
|  | 2020-2022 plan total | 3620000 | 3620000 | 0
| 22. Other / not listed | 2019 plan |  |  |  | N/A | N/A | Loss of Energy Supplies. | 2602297.79 | 2.81 | N/A - this initiative does not address any other risk drivers | New | D. 19-08-027 | GRC | N/A - this initiative is not associated with a specific regulation | N/A - this initiative is not associated with a specific rule | BVPP Reliability Upgrades. Upgrades power plant electronic controls, emissions monitoring systems, catalyst reliability, and engine performance.
2019 actual
|  | 2020 | 925484.5 | 925484.5 | 0
|  | 2021 | 925484.5 | 925484.5 | 0
|  | 2022 | 0 | 0 | 0
|  | 2020-2022 plan total | 1850969 | 1850969 | 0
| 23. Other / not listed | 2019 plan | [14 empty] | Construct an Energy Storage Facility within BVES’s Service Territory. Costs not reflected in this filing as the project is still under consideration. Future WMPs will present firm amounts.
2019 actual
|  | 2020 |  |  | 0
|  | 2021 |  |  | 0
|  | 2022 |  |  | 0
|  | 2020-2022 plan total |  |  | 0

## Table 24
Table 24: Asset management and inspections
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. Detailed inspections of distribution electric lines and equipment | 2019 plan | Bear Valley Electric Service has not specified a wildfire mitigation asset management and inspections initiative for detailed inspections of distribution lines and equipment. BVES's distribution inspection initiatives are best captured in Table 24 Item 11. Patrol inspections of distribution lines and equipment
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Detailed inspections of transmission electric lines and equipment | 2019 plan | Bear Valley Electric Service does not have any transmission lines or equipment as all of BVES's lines are below 65 kV.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Improvement of inspections | 2019 plan | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | All types of equipment failure; Contact from object | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | New in 2019 | CA GO 95 & 165 | N/A - Elements already captured in other relevant programs | In compliance with Regulation | GO 95 & 165 | Improvements of Bear Valley Electric Service's inspections have already been captured in other initiatives
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Infrared inspections of distribution electric lines and equipment | 2019 plan | 96073 |  | 96073 | 70.27 | 1367.198 | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 151260.94 | 1.21 | Wildfire-Significant Loss of Property | Existing | GRC | N/A - this is an existing initiative | Exceeding | GO-95 | Contract Exacter Services. Conduct survey of BVES overhead system on 3-year cycle using infrared, ultrasonic and EMI sensors. Approximately 1/3 of OH system surveyed each year.” to read: “Contract Exacter Services. Conducted survey of BVES overhead system using infrared, ultrasonic and EMI sensors.
|  | 2019 actual | 60104 |  | 60104 | 70.27 | 855.3294
|  | 2020 | 0 |  | 0 | 70.27 | 0
|  | 2021 | 0 |  | 0 | 70.27 | 0
|  | 2022 | 0 |  | 0 | 70.27 | 0
|  | 2020-2022 plan total | 0 |  | 0 | 210.81 | 0
| 5. Infrared inspections of transmission electric lines and equipment | 2019 plan | Bear Valley Electric Service does not have any transmission lines or equipment as all of BVES's lines are below 65 kV.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Intrusive pole inspections | 2019 plan | Test all poles to loading standards, GO95 requirements, intrusive inspection criteria and age and then, replaces or remediates non-compliant poles. Covered under table 23 section 6.
2019 actual
2020
2021
2022
2020-2022 plan total
| 7. LiDAR inspections of distribution electric lines and equipment | 2019 plan | 220000 | 0 | 220000 | 632.43 | 347.8646 | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 1145870.45 | 3.05 | Wildfire-Significant Loss of Property | New | N/A - this is a new initiative | WMP Memorandum Account | Exceeding | GO-165 | Conduct LiDAR surveys of BVES overhead system on a semi-annual basis.
|  | 2019 actual | 0 | 0 | 0 | - | -
|  | 2020 | 240000 | 0 | 240000 | 632.43 | 379.4886
|  | 2021 | 240000 | 0 | 240000 | 632.43 | 379.4886
|  | 2022 | 240000 | 0 | 240000 | 632.43 | 379.4886
|  | 2020-2022 plan total | 720000 | 0 | 720000 | 1897.29 | 379.4886
| 8. LiDAR inspections of transmission electric lines and equipment | 2019 plan | Bear Valley Electric Service does not have any transmission lines or equipment as all of BVES's lines are below 65 kV.
2019 actual
2020
2021
2022
2020-2022 plan total
| 9. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | Bear Valley Electric Service does not have any wildfire mitigation asset management and inspection initiatives focused on other discretionary inspections of distribution electric lines and equipment beyond inspections mandated by rules and regulations at this time that have not been captured in other initiatives.
2019 actual
2020
2021
2022
2020-2022 plan total
| 10. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | Bear Valley Electric Service does not have any transmission lines or equipment as all of BVES's lines are below 65 kV.
2019 actual
2020
2021
2022
2020-2022 plan total
| 11. Patrol inspections of distribution electric lines and equipment | 2019 plan | 90000 | - | 90000 | 632.43 | 0 | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 1024621.77 | 7.27 | N/A - all risk drivers have been captured in the Ignition probability drivers targeted | New | N/A - this is a new initiative | WMP Memorandum Account. | Exceeding | GO-165 | Conduct annual 2nd Ground Patrol of overhead facilities by 3rd party. This is in addition to BVES GO-165 annual ground patrol.
|  | 2019 actual | 0 | 0 | 0 | - | 0
|  | 2020 | 90000 | 0 | 90000 | 632.43 | 142.3082
|  | 2021 | 90000 | 0 | 90000 | 632.43 | 142.3082
|  | 2022 | 90000 | 0 | 90000 | 632.43 | 142.3082
|  | 2020-2022 plan total | 270000 | 0 | 270000 | 1897.29 | 142.3082
| 12. Patrol inspections of transmission electric lines and equipment | 2019 plan | Bear Valley Electric Service does not have any transmission lines or equipment as all of BVES's lines are below 65 kV.
2019 actual
2020
2021
2022
2020-2022 plan total
| 13. Pole loading assessment program to determine safety factor | 2019 plan | Bear Valley Electric Service's wildfire mitigation asset management and inspections pole loading assessment program to determine safety factor is fully captured in Table 24 Initiative 6. Intrusive pole inspections.
2019 actual
2020
2021
2022
2020-2022 plan total
| 14. Quality assurance / quality control of inspections | 2019 plan | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | All | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | Existing | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | General initiative and best practices applied to and accounted for in other relevant initiatives
2019 actual
2020
2021
2022
2020-2022 plan total
| 15. Substation inspections | 2019 plan | Bear Valley Electric Service's substation inspections are fully captured in Table 24 Item 11. Patrol inspections of distribution electric lines and equipment
2019 actual
2020
2021
2022
2020-2022 plan total
| 16. Other / not listed | 2019 plan | $ 105,566.00 | $ - | $ 105,566.00 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 1145870.45 | 6.93 | N/A - all risk drivers have been captured in the Ignition probability drivers targeted | Existing | D. 19-08-027 | GRC | N/A - this initiative is not associated with specific regulations | N/A - this initiative is not associated with specific regulations | Electrical Preventative Maintenance Program. Program to conduct preventive maintenance and safety checks on major substation and field equipment. RSE is an estimate based on latest available risk assessment.
|  | 2019 actual | $ 32,395.00 | $ - | $ 32,395.00
|  | 2020 | $ 105,566.67 | $ - | $ 105,566.67
|  | 2021 | $ 107,678.00 | $ - | $ 107,678.00
|  | 2022 | $ 109,831.56 | $ - | $ 109,831.56
|  | 2020-2022 plan total | $ 323,076.23 | $ - | $ 323,076.23

## Table 25
Table 25: Vegetation management and inspections
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. Additional efforts to manage community and environmental impacts | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation vegetation management and inspection initiative dedicated to this effort at this time. BVES recognizes that additional efforts to manage community and environmental impacts are critical to reducing wildfire risk and conducts such efforts on an as-needed basis, as well as incorporating additional efforts within other programs such as those in Table 29 and Table 30.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Detailed inspections of vegetation around distribution electric lines and equipment | 2019 plan | 1000000 | 0 | 1000000 | N/A - this is a System Wide initiative | N/A - this is a System Wide initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 872292.38 | 0.27 | Wildfire-Significant Loss of Property | Existing | D. 19-08-027 | FHPMA (not new) | Exceeding | GO-95 | Increases vegetation clearances, criterial for tree removals, and eliminates overhang on sub-transmission. These are above the 2017 baseline vegetation clearances that were in effect before CPUC Decision 17-12-024 was adopted.
|  | 2019 actual | 902447 | 0 | 902447
|  | 2020 | 2600000 | 0 | 2600000
|  | 2021 | 2600000 | 0 | 2600000
|  | 2022 | 2600000 | 0 | 2600000
|  | 2020-2022 plan total | 7800000 | 0 | 7800000
| 3. Detailed inspections of vegetation around transmission electric lines and equipment | 2019 plan | Bear Valley Electric Service does not have any transmission lines or equipment as all of BVES's lines are below 65 kV.
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Emergency response vegetation management due to red flag warning or other urgent conditions | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation vegetation management and inspection initiative dedicated to this effort at this time. BVES recognizes that emergency response vegetation management due to red flag warnings or other urgent conditions are critical to reducing wildfire risk and has already incorporated these efforts into BVES's existing Emergency Response and Preparedness Plan as well as the initiatives described in Table 26 Grid Operations and Protocols.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Fuel management and reduction of “slash” from vegetation management activities | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation vegetation management and inspection initiative dedicated to this effort at this time. Fuel management and reduction of "slash" from vegetation management activities have been incorporated into BVES's ongoing and newly proposed vegetation management initiatives as described in Table 25.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Improvement of inspections | 2019 plan | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | Contact from object | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | Reduces escalation should an ignition event occur through removal of fuel | Existing | 2017 GRC & 2019 WMP | N/A - Elements already captured in other relevant initiatives | In compliance with Regulation | GO95 | Program incorporated new requirements in 2019
2019 actual
2020
2021
2022
2020-2022 plan total
| 7. LiDAR inspections of vegetation around distribution electric lines and equipment | 2019 plan | Bear Valley Electric Service's LiDAR inspections of vegetation around distribution electric lines and equipment are captured in Table 24 Initiative 7. LiDAR inspections of distribution electric lines and equipment.
2019 actual
2020
2021
2022
2020-2022 plan total
| 8. LiDAR inspections of vegetation around transmission electric lines and equipment | 2019 plan | Bear Valley Electric Service does not have any transmission lines or equipment as all of BVES's lines are below 65 kV.
2019 actual
2020
2021
2022
2020-2022 plan total
| 9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | Bear Valley Electric Service does not have any other discretionary inspections of vegetation around distribution electric lines and equipment beyond inspections mandated by rules and regulations and other described initiatives at this time.
2019 actual
2020
2021
2022
2020-2022 plan total
| 10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | Bear Valley Electric Service does not have any transmission lines or equipment as all of BVES's lines are below 65 kV.
2019 actual
2020
2021
2022
2020-2022 plan total
| 11. Patrol inspections of vegetation around distribution electric lines and equipment | 2019 plan | Bear Valley Electric Service's patrol inspections of vegetation around distribution electric lines and equipment are fully captured in Table 25 Initiative 2. Detailed inspection of vegetation around distribution electric lines and equipment and Table 24 Initiative 11. Patrol inspections of distribution electric lines and equipment.
2019 actual
2020
2021
2022
2020-2022 plan total
| 12. Patrol inspections of vegetation around transmission electric lines and equipment | 2019 plan | Bear Valley Electric Service does not have any transmission lines or equipment as all of BVES's lines are below 65 kV.
2019 actual
2020
2021
2022
2020-2022 plan total
| 13. Quality assurance / quality control of inspections | 2019 plan | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | All | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | Existing | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | N/A - Elements already captured in other relevant initiatives | General initiative and best practices applied to and accounted for in other relevant initiatives
2019 actual
2020
2021
2022
2020-2022 plan total
| 14. Recruiting and training of vegetation management personnel | 2019 plan | 0 | 0 | 0 | N/A - this is a System Wide initiative | N/A - this is a System Wide initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 151260.94 | 0.67 | Wildfire-Significant Loss of Property | New | N/A - this is a new initiative | WMP Memorandum Account | Exceeding | GO95 | Places a full-time contract utility forester as part of the BVES team. The job duties of the contract forester would include: Inspections: Inspect and evaluate circuits for hot spot locations, hazard tree identification and outage investigations. Auditing: Perform site-specific work audits to ensure contractors are performing within the specifications set forth by BVES. Customer Contacts/Issue Resolution: initiate or follow up in a timely and professional manner on all customer issues that may arise in a manner that will support the policies and procedures of BVES. This includes customer notifications, permit negotiations, conflict resolution, outage support/investigations and providing shared resources to construction, substation, lines and/or various work groups related to BVES’s Vegetation Management group. Administrative: Perform data entry, spreadsheet work, monitor crew activity sheets, track completed work, capture photo documentation of specific conditions and other administrative tasks as needed. Developing Work Plans: Develop work plans that specify the pruning and removal requirements to maintain BVES ROWs. These plans will be developed in an efficient and straightforward manner for a seamless transition to the tree contractors. Specialized Projects: Develop and manage specialized projects with an emphasis on reliability and risk management. Perform enhanced outage investigations, integrated storm hardening projects, performed risk assessment and prioritization studies, developed storm response protocols and implemented hazard tree programs that are focused on improving system safety. Contractor Safety Observations: Observe contractors as they work and provide safety behavior modification to help ensure a program that is best in class not only in vegetation management, but safety as well. RSE is an estimate based on latest available risk assessment.
|  | 2019 actual | 0 | 0 | 0
|  | 2020 | 145000 | 0 | 145000
|  | 2021 | 147900 | 0 | 147900
|  | 2022 | 150858 | 0 | 150858
|  | 2020-2022 plan total | 443758 | 0 | 443758
| 15. Remediation of at-risk species | 2019 plan | Remediation of at-risk species is a subset to the company’s vegetation management practices to achieve clearances around electric lines and equipment as described in Table 25, particularly Table 24 Item 14. As such, Bear Valley Electric Service does not have a specific wildfire mitigation initiative for remediation of at-risk species at this time.
2019 actual
2020
2021
2022
2020-2022 plan total
| 16. Removal and remediation of trees with strike potential to electric lines and equipment | 2019 plan | Removal and remediation of trees with strike potential to electric lines and equipment is a subset to the company’s vegetation management practices to achieve clearances around electric lines and equipment as described in Table 25, particularly Table 24 Item 14. As such, Bear Valley Electric Service does not have a specific wildfire mitigation initiative for removal and remediation of trees with strike potential at this time.
2019 actual
2020
2021
2022
2020-2022 plan total
| 17. Substation inspections | 2019 plan | Substation vegetation management is a subset to the company’s overall vegetation management initiatives as described in Table 25.
2019 actual
2020
2021
2022
2020-2022 plan total
| 18. Substation vegetation management | 2019 plan | Substation inspections are a subset to the company’s overall vegetation management inspections as described in Table 25 Initiatives 2. and 14.
2019 actual
2020
2021
2022
2020-2022 plan total
| 19. Vegetation inventory system | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation initiative dedicated to the creation and management of a vegetation inventory system at this time. The company's utility forester, as described in Table 25 Item 14., maintains such a system.
2019 actual
2020
2021
2022
2020-2022 plan total
| 20. Vegetation management to achieve clearances around electric lines and equipment | 2019 plan | Vegetation management to achieve clearances around electric lines and equipment is captured in Table 25 Items 2. and 14.
2019 actual
2020
2021
2022
2020-2022 plan total
| 21. Other / not listed | 2019 plan | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives | N/A - BVES does not have any other or unlisted vegetation management initiatives
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 26
Table 26: Grid operations and protocols
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. Automatic recloser operations | 2019 plan | 300000 | 300000 | 0 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 1115048.65 | 3.72 | Wildfire-Significant Loss of Property | Existing | D. 19-08-027 | GRC | N/A - this initiative is a non-standard operating practice unassociated with any specific regulation | N/A - this initiative is a non-standard operating practice unassociated with any specific regulation | Automatic Recloser Upgrades. Recloser replacement to reduce electrical sparking, while also helping mitigate power outages and equipment damage. Estimated 33% completion in 2019.
|  | 2019 actual | 290458.75 | 290458.75 | 0
|  | 2020 | - | - | 0
|  | 2021 | - | 0 | 0
|  | 2022 | - | 0 | 0
|  | 2020-2022 plan total | 0 | 0 | 0
| 2. Crew-accompanying ignition prevention and suppression resources and services | 2019 plan | Bear Valley Electric Service does not currently deploy crew-accompanying ignition prevention and suppression resources and services as part of its routine operational practices. When an emergency occurs, BVES communicates and collaborates with local emergency response teams as described in Section 5.3.9, which can include crew-accompanying ignition prevention and suppression resources and services. Additionally, during elevated risk conditions or during fire season, BVES leverages specific work practices and protocols and makes available specific resources and tools for use by operations personnel as included in Table 26. However, BVES does not currently have a specific grid operations and protocols wildfire mitigation initiative focused on crew-accompanying ignition prevention and suppression resources and services. The use of these services will be re-evaluated and considered for future incorporation as part of the annual WMP review process.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Personnel work procedures and training in conditions of elevated fire risk | 2019 plan | 42000 | 0 | 42000 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 146466.53 | 2.23 | Wildfire-Significant Loss of Property | Existing | D. 19-08-027 | GRC | N/A - this initiative is a non-standard operating practice unassociated with any specific regulation | N/A - this initiative is a non-standard operating practice unassociated with any specific regulation | Wildfire Infrastructure Protection Teams. Roles and responsibilities for staff to respond to protect system infrastructure in case of emergencies.
|  | 2019 actual | 0 | 0 | 0
|  | 2020 | 42000 | 0 | 42000
|  | 2021 | 42840 | 0 | 42840
|  | 2022 | 43696.8 | 0 | 43696.8
|  | 2020-2022 plan total | 128536.8 | 0 | 128536.8
| 4. Protocols for PSPS re-energization | 2019 plan | Bear Valley Electric Service considers re-energization after a PSPS event to be a subset of outage restoration and re-energization protocols generally included in Table 26. Therefore, BVES does not have a separate protocol for PSPS.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. PSPS events and mitigation of PSPS impacts | 2019 plan | 42000 | 0 | 42000 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | All | 777385.29 | 18.5092 | Wildfire-Significant Loss of Property | Existing/New | D. 19-08-027 | GRC and Fire Hazard Prevt. Memorandum Account | In compliance | R.18-12-005 | PSPS Protocols. Protocols and procedures to respond to and recover from de-energization events, which proactively prevent wildfires. Costs partially recovered. RSE is an estimate based on latest risk assessment.
|  | 2019 actual | 0 | 0 | 0
|  | 2020 | 42000 | 0 | 42000
|  | 2021 | 42000 | 0 | 42000
|  | 2022 | 42000 | 0 | 42000
|  | 2020-2022 plan total | 126000 | 0 | 126000
| 6. Stationed and on-call ignition prevention and suppression resources and services | 2019 plan | Bear Valley Electric Service does not currently have stationed and on-call ignition prevention and suppression resources and services not captured in existing initiatives.
2019 actual
2020
2021
2022
2020-2022 plan total
| 7. Other / not listed | 2019 plan | N/A - costs recovered in BVES' General Rate Case A.17-05-004. | N/A - costs recovered in BVES' General Rate Case A.17-05-004. | N/A - costs recovered in BVES' General Rate Case A.17-05-004. | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | 1022629.33 | N/A - this initiative is not associated with a specific Risk-Spend Efficiency | Wildfire-Significant Loss of Property | Existing | D. 19-08-027 | GRC | N/A - this initiative is a non-standard operating practice unassociated with any specific regulation | N/A - this initiative is not associated with any specific regulation | Operational Considerations/Special Work Procedures. Operational procedures that are conditions-based to optimize the distribution system for wildfire mitigation. Costs recovered in BVES' General Rate Case A.17-05-004.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 27
Table 27: Data governance
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. Centralized repository for data | 2019 plan | 46382.29 | 0 | 46382.29 | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | All | 148458.96 | 3.2 | Wildfire-Significant Loss of Property. | Existing | D. 19-08-027 | GRC | N/A - this initiative is unassociated with any specific regulation | N/A - this initiative is unassociated with any specific regulation | GIS Data Collection & Sharing. Maintain and share Geographic Information System (GIS) database on system infrastructure for asset management and planning with key stakeholders.
|  | 2019 actual | 46382.29 | 0 | 46382.29
|  | 2020 | 46382.29 | 0 | 46382.29
|  | 2021 | 46382.29 | 0 | 46382.29
|  | 2022 | 46382.29 | 0 | 46382.29
|  | 2020-2022 plan total | 139146.87 | 0 | 139146.87
| 2. Collaborative research on utility ignition and/or wildfire | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation data governance plan focused on collaborative research on utility ignition and/or wildfire at this time. The company generally collaborates with Mutual Aid Partners and first responders to develop protocols, procedures, and communication plans to prevent, manage, and respond to utility ignition and/or wildfire.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Documentation and disclosure of wildfire-related data and algorithms | 2019 plan | Bear Valley Electric Service does not have a specific data governance wildfire mitigation program focused on documentation and disclosure of wildfire-related data and algorithms that maps to the tracking and level of detail requested in this table at this time.
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Tracking and analysis of near miss data | 2019 plan | Bear Valley Electric Service does not have a specific wildfire mitigation data governance initiative focused on tracking and analysis of near-miss data that maps to the tracking and level of detail requested in this table at this time.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Other / not listed | 2019 plan | Bear Valley Electric Service does not have any other wildfire mitigation data governance initiatives at this time.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 28
Table 28: Resource allocation methodology
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. Allocation methodology development and application | 2019 plan | N/A - While BVES is committed to the continued development and improvement of the company’s risk-based decision making framework, many of the elements requested in this 2020 CA WMP filing may not be applicable to Bear Valley Electric Service, specifically many of the components requested in this section. Bear Valley Electric Service cannot provide information regarding BVES's wildifre mitigation resouce allocation methodology focused on allocation methodology development and application to the level of tracking and detail requested in this table at this time. At the guidance of the Wildfire Safety Division of the California Public Utilities Commission, these elements are marked “N/A" to indicate "does not apply" or "not applicable," with supplementary explanations where applicable througout the company's filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Risk reduction scenario development and analysis | 2019 plan | N/A - While BVES is committed to the continued development and improvement of the company’s risk-based decision making framework, many of the elements requested in this 2020 CA WMP filing may not be applicable to Bear Valley Electric Service, specifically many of the components requested in this section. Bear Valley Electric Service cannot provide information regarding BVES's wildifre mitigation resouce allocation methodology focused on risk reduction scenario development and analysis to the level of tracking and detail requested in this table at this time. At the guidance of the Wildfire Safety Division of the California Public Utilities Commission, these elements are marked “N/A" to indicate "does not apply" or "not applicable," with supplementary explanations where applicable througout the company's filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Risk spend efficiency analysis | 2019 plan | N/A - While BVES is committed to the continued development and improvement of the company’s risk-based decision making framework, many of the elements requested in this 2020 CA WMP filing may not be applicable to Bear Valley Electric Service, specifically many of the components requested in this section. Bear Valley Electric Service cannot provide information regarding BVES's wildifre mitigation resouce allocation methodology focused on risk spend efficiency analysis to the level of tracking and detail requested in this table at this time. At the guidance of the Wildfire Safety Division of the California Public Utilities Commission, these elements are marked “N/A" to indicate "does not apply" or "not applicable," with supplementary explanations where applicable througout the company's filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Other / not listed | 2019 plan | N/A - While BVES is committed to the continued development and improvement of the company’s risk-based decision making framework, many of the elements requested in this 2020 CA WMP filing may not be applicable to Bear Valley Electric Service, specifically many of the components requested in this section. Bear Valley Electric Service cannot provide information regarding BVES's wildifre mitigation resouce allocation methodology focused on any other unlisted initiative(s) to the level of tracking and detail requested in this table at this time. At the guidance of the Wildfire Safety Division of the California Public Utilities Commission, these elements are marked “N/A" to indicate "does not apply" or "not applicable," with supplementary explanations where applicable througout the company's filing.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 29
Table 29: Emergency planning and preparedness
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. Adequate and trained workforce for service restoration | 2019 plan | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | N/A - response related | BVES currently has adequate and trained workforce for service restoration. No risk reduction has been calculated since this action is considered a “control”. No RSE was calculated due no incremental cost being incurred or planned to date. | N/A - as a System Wide Initiative, this initiative does not have a specific risk-spend efficiency | Reduces impact to customers and comunity from an event causing interrupting of service; reduces risk of escalation | Existing | GRC | N/A - this is an Existing initiative | In compliance | GO 166 | N/A - no additional comments
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Community outreach, public awareness, and communications efforts | 2019 plan | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object | N/A - as a System Wide Initiative, this initiative does not have a specified risk reduction | N/A - as a System Wide Initiative, this initiative does not have a specific risk-spend efficiency | Reduces impact to customers and comunity from an event causing interrupting of service; reduces risk of escalation | Existing | GRC | N/A - this is an Existing initiative | In compliance | GO 167 | N/A - no additional comments
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Customer support in emergencies | 2019 plan | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | N/A - response related | BVES has an Emergency Response Plan that addresses customer support in emergencies and a disaster relief plan. No risk reduction has been calculated since this action is considered a “control”. No RSE was calculated due no incremental cost being incurred or planned to date. BVES will continue to review this program and may in future WMPs include enhancements that may incur incremental costs. | N/A - as a System Wide Initiative, this initiative does not have a specific risk-spend efficiency | Reduces impact to customers and comunity from an event causing interrupting of service; reduces risk of escalation | Existing | GRC | N/A - this is an Existing initiative | In compliance | R.18-12-005 | N/A - no additional comments
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Disaster and emergency preparedness plan | 2019 plan | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | Contact from object, all types of equipment/facility failure, wire-to-wire contact/contamination | BVES has an Emergency Response Plan for service restoration and a disaster relief plans in place. No risk reduction has been calculated since this action is considered a “control”. No RSE was calculated due no incremental cost being incurred or planned to date. BVES will continue to review this program and may in future WMPs include enhancements that may incur incremental costs. | N/A - this initiative does not have a specific Risk-spend efficiency | Wildfire-Significant Loss of Property | Existing | D. 19-08-027 | N/A | In compliance | GO 166 | Emergency Reporting & Procedures. Protocols and procedures for staff to respond to faults, emergencies, outages, dissaster events (such as earthquake, wildfire, etc.), etc.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Preparedness and planning for service restoration | 2019 plan | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | N/A - response related | BVES has an Emergency Response Plan for service restoration in place. No risk reduction has been calculated since this action is considered a “control”. No RSE was calculated due no incremental cost being incurred or planned to date. BVES will continue to review this program and may in future WMPs include enhancements that may incur incremental costs. | N/A - this initiative does not have a specific Risk-spend efficiency | Wildfire-Significant Loss of Property | Existing | D. 19-08-027 | CEMA if applicable | In compliance | GO 166 | Post-Incident Recovery, Restoration & Remediation. Protocols and procedures to respond to and recover from any wildfire or related emergency events.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Protocols in place to learn from wildfire events | 2019 plan | Bear Valley Electric Service leverages the protocols included in the company’s Emergency Preparedness and Response Plan to learn from wildfire events in the same manner BVES learns from any emergency event. Therefore, Bear Valley Electric Service does not have specific protocols in place to learn from wildfire events that are not already covered in a previous program.
2019 actual
2020
2021
2022
2020-2022 plan total
| 7. Other / not listed | 2019 plan | Bear Valley Electric Service does not have emergency planning and preparedness initiatives other than those listed above at this time.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 30
Table 30: Stakeholder cooperation and community engagement
| Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
| 1. Community engagement | 2019 plan | Bear Valley Electric Service does not have a community engagement program specific to wildfire mitigation at this time. BVES values community engagement as a wildfire risk mitigation strategy and has incorporated community engagement as a component of its overall Emergency Preparedness and Response Programs as included in Section 5.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Cooperation and best practice sharing with agencies outside CA | 2019 plan | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is not a specifically budgeted program | N/A - this is a System Wide Initiative | N/A - this is a System Wide Initiative | This initiative targets all ignition probabilty drivers | N/A - as a System Wide Initiative, this initiative does not have a specified risk reduction | N/A - as a System Wide Initiative, this initiative does not have a specific risk-spend efficiency | Reduces risk of escalation through support of accelerated restoration | Existing | N/A - none | N/A - this is an Existing initiative | N/A - there is not a clear threshold for compliance for this initiative | N/A - none | N/A - none
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Cooperation with suppression agencies | 2019 plan | During emergency situations, Bear Valley Electric Service's [emergency management group] communicates and collaborates with federal and state emergency responders and mutual assistance groups, including fire suppression agencies. The emergency manager has contact information for [state, county and tribal emergency managers, the state’s Emergency Operations Center Emergency Support Functions (ESF) personnel, and the Geographic Area Coordination Centers dispatch centers for fire-related emergency response. ] Bear Valley Electric Service views cooperation with suppression agencies as a component of the company’s Emergency Planning and Preparedness Programs outlined in Section X and does not have a separate program for cooperation with suppression agencies specific to this Wildfire Mitigation Plan at this time as such.
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Forest service and fuel reduction cooperation and joint roadmap | 2019 plan | While collaboration such as this is critical to the overall reduction of wildfire risk in the state of CA, Bear Valley Electric Service does not have program dedicated to cooperation with the forest service and fuel reduction and the development of a joint roadmap specific to this Wildfire Mitigation Plan . BVES views these efforts on an as-needed basis and incorporates additional efforts to manage community environments within other programs, such as those included in Section 5 and the company’s overall vegetation management and inspections programs described in Section 5.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Other / not listed | 2019 plan | Bear Valley Electric Service does not have stakeholder cooperation and community engagement initiatives other than those listed above.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 31
Table 31: Change in drivers of ignition probability taking into account planned initiatives, for each year of plan
| Incident type by ignition probability driver | Detailed risk driver | Are near misses tracked? | Number of incidents per year |  |  | Average percentage likelihood of ignition per incident |  |  | Number of ignitions per year
|  |  |  | 2020 | 2021 | 2022 | 2020 | 2021 | 2022 | 2020 | 2021 | 2022
| Contact from object | All types of object contact | Y | 4 | 4 | 2 | 0% | 0% | 0% | 0 | 0 | 0
|  | Animal contact | Y | 1 | 1 | 0 | 0% | 0% | 0% | 0 | 0 | 0
|  | Balloon contact | Y | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
|  | Vegetation contact | Y | 3 | 3 | 2 | 0% | 0% | 0% | 0 | 0 | 0
|  | Vehicle contact | Y | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
| All types of equipment / facility failure | All types | Y | 16 | 14 | 11 | 0% | 0% | 0% | 0 | 0 | 0
|  | Capacitor bank failure | Y | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
|  | Conductor failure—all | Y | 3 | 3 | 2 | 0% | 0% | 0% | 0 | 0 | 0
|  | Conductor failure—wires down | Y | 3 | 3 | 2 | 0% | 0% | 0% | 0 | 0 | 0
|  | Fuse failure—all | Y | 4 | 3 | 3 | 0% | 0% | 0% | 0 | 0 | 0
|  | Fuse failure—conventional blown fuse | Y | 4 | 3 | 3 | 0% | 0% | 0% | 0 | 0 | 0
|  | Lightning arrestor failure | Y | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
|  | Switch failure | Y | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
|  | Transformer failure | Y | 2 | 2 | 1 | 0% | 0% | 0% | 0 | 0 | 0
| Wire-to-wire contact / contamination |  | Y | 2 | 1 | 0 | 0% | 0% | 0% | 0 | 0 | 0
| Other |  | Y | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0

## >>WMP Section 6
Section 6 of the WMP narrative does not require reportable tables from Attachment 1.
Please see BVES's 2020 Final Action Statement WMP for developed responses.
This tab is informative only

## Attachment 4 (WMP Metrics) (hidden)
Metric toTrack | Party Responsible | Item/Table # | Data Owner/Location | Tracking Set Up?
Number of Level 1, 2, and 3 findings per mile of circuit in HFTD, and per total miles of circuit for each of the following inspection types: 1. Patrol inspections 2. Detailed inspections 3. Other inspection types | Paul & Jeff (BVES) | Table 1 Item 1
Percentage of right-of-way with noncompliant clearance based on applicable rules and regulations at the time of inspection | Paul & Jeff (BVES) | Table 1 Item 2
Percentage of total PSPS predictions that are false positives or false negatives 2 days before a potential PSPS event | Paul & Marc (BVES) | Table 1 Item 3
Number of sectionalizing devices per circuit mile and number of automated grid control equipment in: 1. HFTD 2. Non-HFTD | Eric (BVES) | Table 1 Item 4
Number of circuit hours operated above nameplate capacity in HFTD areas Average % above nameplate capacity when equipment operated above nameplate capacity in HFTD areas | Eric (BVES) | Table 1 Item 5
Dollars per incremental life saved Dollars invested per estimated dollars of rebuilt structures avoided Dollars per customer hour of PSPS avoided | Paul & Marc (BVES) | Table 1 Item 6
Percent of all grid assets in HFTD areas using proven and demonstrated wildfire-resistant equipment | Eric (BVES) | Table 1 Item 7
Percent of residents made aware of PSPS and emergency response procedures in advance of events, according to post-event surveys Percent of residents agreeing to participate in utility wildfire risk-reduction activities (e.g., allowing access to property for utility hazard tree remediation) | Sean (BVES) | Table 1 Item 8
Number of emergency response deficiencies reported by Cal OES, suppression agencies, and other emergency response personnel when plans tested or activated | Paul & Marc (BVES) | Table 1 Item 9
Percent of data requested in SDR and WMP collected in initial submission Number of data elements shared publicly by utilities | Navigant | Table 1 Item 10
Number of all events (such as unplanned outages, faults, conventional blown fuses, etc.) that could result in ignition, by type according to utility- provided list (total) | Paul & Marc (BVES) | Table 2 Item 1a
Number of all events (such as unplanned outages, faults, conventional blown fuses, etc.) that could result in ignition, by type according to utility- provided list (normalized) | Paul & Marc (BVES) | Table 2 Item 1b
Number of wires down per year | Paul (BVES) | Table 2 Item 1c
Number of wires down per year (normalized) | Paul (BVES) | Table 2 Item 1c
Average number of Level 1 findings that could increase the probability of ignition discovered by all inspections per circuit mile per year | Paul & Marc (BVES) | Table 2 Item 2a
Average number of Level 2 findings that could increase the probability of ignition discovered by all inspections per circuit mile per year | Paul & Marc (BVES) | Table 2 Item 2b
Average number of Level 3 findings that could increase the probability of ignition discovered by all inspections per circuit mile per year | Paul & Marc (BVES) | Table 2 Item 2c
Incremental cost per grid-wide 1% reduction in utility ignition in HFTD areas | Paul & Marc (BVES) | Table 2 Item 3a
Incremental cost per grid-wide 1% reduction in utility ignition in HFTD areas | Paul & Marc (BVES) | Table 2 Item 3b
Contracts for future purchases of renewable energy (% of total estimated electricity procurement per year) | Sean (BVES) | Table 2 Item 4a
Percent of customers experiencing PSPS given 95th percentile fire weather conditions along entire grid using utility PSPS decision protocols | Marc & Eric (BVES) | Table 2 Item 5a
Percent of customers experiencing PSPS given 99th percentile fire weather conditions along entire grid using utility PSPS decision protocols | Marc & Eric (BVES) | Table 2 Item 5b
Customer hours of planned outages including PSPS (total) | Marc & Jeff (BVES) | Table 2 Item 6a
Customer hours of planned outages including PSPS (normalized) | Marc & Jeff (BVES) | Table 2 Item 6b
Customer hours of unplanned outages, not including PSPS (total) | Paul (BVES) | Table 2 Item 6c
Customer hours of unplanned outages, not including PSPS (normalized) | Paul (BVES) | Table 2 Item 6d
Increase in System Average Interruption Duration Index (SAIDI) | Paul (BVES) | Table 2 Item 6e
Increase in electric costs to ratepayer due to wildfires (total) | Paul & Sean (BVES) | Table 2 Item 7a
Increase in electric costs to ratepayer due to wildfires (normalized) | Paul &Sean (BVES) | Table 2 Item 7b
Increase in electric costs to ratepayer due to wildfire mitigation activities (total) | Paul & Sean (BVES) | Table 2 Item 7c
Electricity procured from renewable sources (Percentage of total electricity procured per year) | Sean (BVES) | Table 2 Item 8a
Potential impact of ignitions (total); Number of people residing in evacuation zones of wildfires simulated for each ignition per year, based on in-house or contractors’ fire spread models | Sean/Eric (BVES) & Navigant | Table 2 Item 9a
Potential impact of ignitions (normalized); Number of people residing in evacuation zones of wildfires simulated for each Number of people residing in evacuation zones of wildfires simulated for each | Sean/Eric (BVES) & Navigant | Table 2 Item 9b
Potential impact of ignitions in HFTD (subtotal); Number of people residing in evacuation zones of wildfires simulated for each ignition in HFTD per year | Sean/Eric (BVES) & Navigant | Table 2 Item 9c
Potential impact of ignitions in HFTD Zone 1; Number of people residing in evacuation zones of wildfires simulated for each ignition in HFTD Zone 1 per year | Sean/Eric (BVES) & Navigant | Table 2 Item 9ci
Potential impact of ignitions in HFTD Tier 2; Number of people residing in evacuation zones of wildfires simulated for each ignition in HFTD Tier 2 per year | Sean/Eric (BVES) & Navigant | Table 2 Item 9cii
Potential impact of ignitions in HFTD Tier 3; Number of people residing in evacuation zones of wildfires simulated for each ignition in HFTD Tier 3 per year | Sean/Eric (BVES) & Navigant | Table 2 Item 9ciii
Potential impact of ignitions in HFTD (subtotal, normalized) | Navigant | Table 2 Item 9d
Potential impact of ignitions in HFTD Zone 1 (normalized) | Navigant | Table 2 Item 9di
Potential impact of ignitions in HFTD Tier 2 (normalized) | Navigant | Table 2 Item 9dii
Potential impact of ignitions in HFTD Tier 3 (normalized) | Navigant | Table 2 Item 9diii
Potential impact of ignitions in non-HFTD (subtotal) | Navigant | Table 2 Item 9e
Potential impact of ignitions in non-HFTD (normalized) | Navigant | Table 2 Item 9f
Fatalities due to utility- ignited wildfire (total) | Navigant | Table 2 Item 10a
Fatalities due to utility- ignited wildfire (normalized) | Navigant | Table 2 Item 10b
Fatalities due to utility wildfire mitigation activities (total) | Navigant | Table 2 Item 11
OSHA-reportable injuries due to utility wildfire mitigation activities (total) | Marc (BVES) | Table 2 Item 12a
OSHA-reportable injuries due to utility wildfire mitigation activities (normalized) | Marc (BVES) | Table 2 Item 12b
Value of assets destroyed by utility-ignited wildfire (total) | Marc (BVES) | Table 2 Item 13a
Value of assets destroyed by utility-ignited wildfire (normalized) | Marc (BVES) | Table 2 Item 13b
Number of structures destroyed by utility- ignited wildfire (total) | Marc (BVES) | Table 2 Item 14a
Number of structures destroyed by utility- ignited wildfire (normalized) | Marc (BVES) | Table 2 Item 14b
Number of people residing in evacuation zone of utility-ignited wildfire (total) | Marc (BVES) | Table 2 Item 15a
Number of people residing in evacuation zone of utility-ignited wildfire (normalized) | Marc (BVES) | Table 2 Item 15b
Impact of evacuations for utility-ignited wildfire (total) | Marc (BVES) | Table 2 Item 15c
Impact of evacuations for utility-ignited wildfire (normalized) | Marc (BVES) | Table 2 Item 15d
Acreage burned by utility-ignited wildfire (total) | Marc (BVES) | Table 2 Item 16a
Acreage burned by utility-ignited wildfire (normalized) | Marc (BVES) | Table 2 Item 16b
Number of ignitions (total) according to existing ignition data reporting requirement | Marc (BVES) | Table 2 Item 17a
Number of ignitions (normalized) | Marc (BVES) | Table 2 Item 17b
Number of ignitions in HFTD (subtotal) | Marc (BVES) | Table 2 Item 17c
Number of ignitions in HFTD Zone 1 | Marc (BVES) | Table 2 Item 17ci
Number of ignitions in HFTD Tier 2 | Marc (BVES) | Table 2 Item 17cii
Number of ignitions in HFTD Tier 3 | Marc (BVES) | Table 2 Item 17ciii
Number of ignitions in HFTD (subtotal, normalized) | Marc (BVES) | Table 2 Item 17d
Number of ignitions in HFTD Zone 1, (normalized) | Marc (BVES) | Table 2 Item 17di
Number of ignitions in HFTD Tier 2 (normalized) | Marc (BVES) | Table 2 Item 17dii
Number of ignitions in HFTD Tier 3 (normalized) | Marc (BVES) | Table 2 Item 17diii
Number of ignitions in non-HFTD (subtotal) | Marc (BVES) | Table 2 Item 17e
Number of ignitions in non-HFTD (normalized) | Marc (BVES) | Table 2 Item 17f
GHG emissions from utility-ignited wildfires (total); Estimated tons of carbon dioxide equivalent emitted per year | Marc (BVES) | Table 2 Item 18a
GHG emissions from utility-ignited wildfires (normalized); Estimated tons of carbon dioxide equivalent emitted per RFW circuit mile day per year | Marc (BVES) | Table 2 Item 18b
Critical transportation infrastructure impacted due to PSPS; Driver and rider-hours lost (in ridership per hour multiplied by incremental increase in commute time by hours closed) per year | Marc (BVES) | Table 2 Item 19a
Major roads impacted due to PSPS (normalized); Driver and rider-hours lost (in ridership per hour multiplied by incremental increase in commute time by hours closed) per RFW circuit mile day per year | Marc (BVES) | Table 2 Item 19b
Critical infrastructure impacted by PSPS; Number of critical infrastructure locations impacted per hour multiplied by hours offline per year | Marc (BVES) | Table 2 Item 20a
Critical infrastructure impacted by PSPS (normalized); Number of critical infrastructure locations impacted per hour multiplied by hours offline per RFW circuit mile day per year | Marc (BVES) | Table 2 Item 20b